## Read me
Project Atlas: integrated plan workbook
HR policy and process documentation program
Program dates: 2026-10-12 to 2027-10-08. Sponsor: Chief People Officer (CHRO). Program manager: HR Program Manager (PMO lead). Plan version 1.0.
Exported from the Hire-to-Retire Atlas on 2026-10-01. The Atlas is the live source of truth for status and approvals; this workbook is a snapshot for planning and reporting.
How to use it
1. Plan sheet: one row per item (57 policies, 97 processes, 284 legal obligations). Yellow columns are inputs: Status, Owner, Go-live override and Notes.
2. Go live (current) uses the override when one is entered, otherwise the planned date. Overdue and Days late are formulas against today's date.
3. Dashboard sheet: every number is a formula over the Plan sheet, so it updates as you change statuses.
4. Status values: Not started, Drafting, In review, Approved, Live, Not applicable. Approved, Live and Not applicable count as done.
5. Stage dates come from the plan: discover 2 weeks, draft 3, review 2, approve 2, go live 1, skipping the year-end freeze (Dec 21, 2026 to Jan 1, 2027).
Waves
Mobilize: 2026-10-12 to 2026-11-06. Team, charter, tooling, approval chains and a rated baseline of all 438 items.
Wave 1: Must-haves: 2026-11-09 to 2027-02-12. The highest-risk legally required, public-company and semiconductor items in every workstream: policies first, then the programs, notices and controls that depend on them.
Wave 2: Core lifecycle: 2027-02-15 to 2027-05-14. The next tranche of required items, with the bulk of process documentation and country addenda.
Wave 3: Complete coverage: 2027-05-17 to 2027-08-13. The remaining required items, so every legal, public-company and semiconductor item is live.
Wave 4: Embed and sustain: 2027-08-16 to 2027-10-08. Best-practice items, the global attestation campaign, audit readiness and handover to business-as-usual owners.
Example row (Plan sheet)
POL-09 Anti-Harassment · Policy · Wave 1 · Governance, Ethics and Employee Relations · go live 29 Jan 2027 · Status: Drafting · Owner: Head of Employee Relations · Notes: Current doc on ER SharePoint; Israel bylaw and India IC addendum missing.

## Dashboard
Dashboard
All figures are formulas over the Plan sheet.
Items | 438
Done (approved, live or not applicable) | 0
Percent done | 0%
Overdue | 0
Due so far | 0
Overdue as share of due | 0%
Calculated rating | Green
Rating thresholds | Red at 15% or more of due items overdue, Amber at 5%. Set by the PMO; change here if the steering committee agrees different ones.
By wave
Wave | Not started | Drafting | In review | Approved | Live | Not applicable | Total | Done | % done | Overdue
Wave 1 | 170 | 0 | 0 | 0 | 0 | 0 | 170 | 0 | 0% | 0
Wave 2 | 146 | 0 | 0 | 0 | 0 | 0 | 146 | 0 | 0% | 0
Wave 3 | 105 | 0 | 0 | 0 | 0 | 0 | 105 | 0 | 0% | 0
Wave 4 | 17 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0% | 0
Total | 438 | 0 | 0 | 0 | 0 | 0 | 438 | 0 | 0% | 0
By workstream
Workstream | Not started | Drafting | In review | Approved | Live | Not applicable | Total | Done | % done | Overdue
Governance, Ethics and Employee Relations | 82 | 0 | 0 | 0 | 0 | 0 | 82 | 0 | 0% | 0
Talent Acquisition | 43 | 0 | 0 | 0 | 0 | 0 | 43 | 0 | 0% | 0
HR Operations and Employee Lifecycle | 75 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0% | 0
Total Rewards and Payroll | 111 | 0 | 0 | 0 | 0 | 0 | 111 | 0 | 0% | 0
Talent, Leave and Engagement | 52 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 0% | 0
HR Data, Safety and Systems | 75 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0% | 0
Total | 438 | 0 | 0 | 0 | 0 | 0 | 438 | 0 | 0% | 0
By type
Type | Not started | Drafting | In review | Approved | Live | Not applicable | Total | Done | % done | Overdue
Policy | 57 | 0 | 0 | 0 | 0 | 0 | 57 | 0 | 0% | 0
Process | 97 | 0 | 0 | 0 | 0 | 0 | 97 | 0 | 0% | 0
Filing | 82 | 0 | 0 | 0 | 0 | 0 | 82 | 0 | 0% | 0
Control | 79 | 0 | 0 | 0 | 0 | 0 | 79 | 0 | 0% | 0
Program | 45 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0% | 0
Notice | 40 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0% | 0
Record | 17 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0% | 0
Committee | 13 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0% | 0
Training | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0% | 0
Total | 438 | 0 | 0 | 0 | 0 | 0 | 438 | 0 | 0% | 0

## Plan
ID | Item | Type | Domain | Tier | Workstream | Wave | Start | Discover done | Draft done | Review done | Approved by | Go live (plan) | Go live (override) | Go live (current) | Status | Owner | Notes | Overdue | Days late
POL-01 | Code of Business Conduct & Ethics | Policy | Governance | Public-company driven | Governance, Ethics and Employee Relations | Wave 1 | 2026-11-09 | 2026-11-20 | 2026-12-11 | 2027-01-08 | 2027-01-22 | 2027-01-29 |  | 2027-01-29 | Not started | Ethics & Compliance (Chief Compliance Officer); HR Employee Relations for people-related sections
POL-02 | Speak Up & Non-Retaliation | Policy | Governance | Public-company driven | Governance, Ethics and Employee Relations | Wave 1 | 2026-11-09 | 2026-11-20 | 2026-12-11 | 2027-01-08 | 2027-01-22 | 2027-01-29 |  | 2027-01-29 | Not started | Ethics & Compliance (hotline and case management); Employee Relations for people-related investigations
POL-03 | Conflicts of Interest & Outside Activities | Policy | Governance | Public-company driven | Governance, Ethics and Employee Relations | Wave 1 | 2026-11-09 | 2026-11-20 | 2026-12-11 | 2027-01-08 | 2027-01-22 | 2027-01-29 |  | 2027-01-29 | Not started | Ethics & Compliance (disclosure program), with Legal (related-person transactions) and HR (outside-employment approvals)
POL-04 | Anti-Bribery & Anti-Corruption (HR aspects) | Policy | Governance | Public-company driven | Governance, Ethics and Employee Relations | Wave 1 | 2026-11-09 | 2026-11-20 | 2026-12-11 | 2027-01-08 | 2027-01-22 | 2027-01-29 |  | 2027-01-29 | Not started | Ethics & Compliance (ABAC program); Talent Acquisition and Employee Relations own the HR controls
POL-05 | Insider Trading | Policy | Governance | Public-company driven | Governance, Ethics and Employee Relations | Wave 1 | 2026-11-09 | 2026-11-20 | 2026-12-11 | 2027-01-08 | 2027-01-22 | 2027-01-29 |  | 2027-01-29 | Not started | Legal (Securities) with Equity Administration (Stock Admin)
POL-06 | Compensation Recovery (Clawback) | Policy | Governance | Public-company driven | Governance, Ethics and Employee Relations | Wave 1 | 2026-11-09 | 2026-11-20 | 2026-12-11 | 2027-01-08 | 2027-01-22 | 2027-01-29 |  | 2027-01-29 | Not started | Total Rewards with Legal and Finance (Controller)
POL-08 | Equal Employment Opportunity | Policy | Relations | Legally required | Governance, Ethics and Employee Relations | Wave 1 | 2026-11-09 | 2026-11-20 | 2026-12-11 | 2027-01-08 | 2027-01-22 | 2027-01-29 |  | 2027-01-29 | Not started | HR (Employee Relations) with Employment Legal; Talent Acquisition for hiring practices
POL-09 | Anti-Harassment | Policy | Relations | Legally required | Governance, Ethics and Employee Relations | Wave 1 | 2026-11-09 | 2026-11-20 | 2026-12-11 | 2027-01-08 | 2027-01-22 | 2027-01-29 |  | 2027-01-29 | Not started | HR (Employee Relations)
POL-16 | Recruitment & Selection | Policy | Recruit | Legally required | Talent Acquisition | Wave 1 | 2026-11-09 | 2026-11-20 | 2026-12-11 | 2027-01-08 | 2027-01-22 | 2027-01-29 |  | 2027-01-29 | Not started | Talent Acquisition (Head of TA)
POL-17 | Background Screening | Policy | Recruit | Legally required | Talent Acquisition | Wave 1 | 2026-11-09 | 2026-11-20 | 2026-12-11 | 2027-01-08 | 2027-01-22 | 2027-01-29 |  | 2027-01-29 | Not started | Talent Acquisition Operations with Legal (Employment and Privacy) and Security
POL-18 | Export Control & Deemed Exports (Employees) | Policy | Recruit | Semiconductor-specific | Talent Acquisition | Wave 1 | 2026-11-09 | 2026-11-20 | 2026-12-11 | 2027-01-08 | 2027-01-22 | 2027-01-29 |  | 2027-01-29 | Not started | Trade Compliance (Export Control Officer) with HR (People Ops, Talent Acquisition, Immigration) and IT/Security
POL-19 | Immigration Sponsorship | Policy | Recruit | Legally required | Talent Acquisition | Wave 1 | 2026-11-09 | 2026-11-20 | 2026-12-11 | 2027-01-08 | 2027-01-22 | 2027-01-29 |  | 2027-01-29 | Not started | Immigration (Global Mobility) with Talent Acquisition and Legal
POL-20 | Contingent Workforce & Worker Classification | Policy | Recruit | Legally required | Talent Acquisition | Wave 1 | 2026-11-09 | 2026-11-20 | 2026-12-11 | 2027-01-08 | 2027-01-22 | 2027-01-29 |  | 2027-01-29 | Not started | People Ops (Contingent Workforce Program) with Procurement and Legal
POL-24 | Pay Equity & Pay Transparency | Policy | Reward | Legally required | Total Rewards and Payroll | Wave 1 | 2026-11-09 | 2026-11-20 | 2026-12-11 | 2027-01-08 | 2027-01-22 | 2027-01-29 |  | 2027-01-29 | Not started | Total Rewards with Employment Legal and HR Analytics
POL-26 | Sales Compensation Governance | Policy | Reward | Legally required | Total Rewards and Payroll | Wave 1 | 2026-11-09 | 2026-11-20 | 2026-12-11 | 2027-01-08 | 2027-01-22 | 2027-01-29 |  | 2027-01-29 | Not started | Sales Operations (plan administration) with Total Rewards (design) and Finance
POL-27 | Equity Grant Policy | Policy | Reward | Public-company driven | Total Rewards and Payroll | Wave 1 | 2026-11-09 | 2026-11-20 | 2026-12-11 | 2027-01-08 | 2027-01-22 | 2027-01-29 |  | 2027-01-29 | Not started | Total Rewards (design) with Stock Admin (administration) and Legal (Securities)
POL-28 | Payroll & Wage Payment | Policy | Reward | Legally required | Total Rewards and Payroll | Wave 1 | 2026-11-09 | 2026-11-20 | 2026-12-11 | 2027-01-08 | 2027-01-22 | 2027-01-29 |  | 2027-01-29 | Not started | Global Payroll with People Ops
POL-29 | Hours of Work, Overtime & Timekeeping | Policy | Reward | Legally required | Total Rewards and Payroll | Wave 1 | 2026-11-09 | 2026-11-20 | 2026-12-11 | 2027-01-08 | 2027-01-22 | 2027-01-29 |  | 2027-01-29 | Not started | Total Rewards (classification) and Global Payroll (timekeeping and overtime pay)
POL-30 | Expense Reimbursement & Remote-Work Stipends | Policy | Reward | Legally required | Total Rewards and Payroll | Wave 1 | 2026-11-09 | 2026-11-20 | 2026-12-11 | 2027-01-08 | 2027-01-22 | 2027-01-29 |  | 2027-01-29 | Not started | Finance (Travel & Expense) with Total Rewards (stipends)
POL-31 | Sign-on, Relocation & Repayment Agreements | Policy | Reward | Legally required | Total Rewards and Payroll | Wave 1 | 2026-11-09 | 2026-11-20 | 2026-12-11 | 2027-01-08 | 2027-01-22 | 2027-01-29 |  | 2027-01-29 | Not started | Total Rewards with Global Mobility and Talent Acquisition
POL-33 | Paid Time Off & Holidays | Policy | Leave | Legally required | Talent, Leave and Engagement | Wave 1 | 2026-11-09 | 2026-11-20 | 2026-12-11 | 2027-01-08 | 2027-01-22 | 2027-01-29 |  | 2027-01-29 | Not started | Total Rewards (Benefits) with People Ops (leave administration)
POL-34 | Sick Leave | Policy | Leave | Legally required | Talent, Leave and Engagement | Wave 1 | 2026-11-09 | 2026-11-20 | 2026-12-11 | 2027-01-08 | 2027-01-22 | 2027-01-29 |  | 2027-01-29 | Not started | People Ops (Leave & Accommodation team)
POL-35 | Leaves of Absence | Policy | Leave | Legally required | Talent, Leave and Engagement | Wave 1 | 2026-11-09 | 2026-11-20 | 2026-12-11 | 2027-01-08 | 2027-01-22 | 2027-01-29 |  | 2027-01-29 | Not started | People Ops (Leave & Accommodation team)
POL-36 | Reasonable Accommodation | Policy | Leave | Legally required | Talent, Leave and Engagement | Wave 1 | 2026-11-09 | 2026-11-20 | 2026-12-11 | 2027-01-08 | 2027-01-22 | 2027-01-29 |  | 2027-01-29 | Not started | People Ops (Leave & Accommodation team) with Employee Relations
POL-37 | Benefits Eligibility | Policy | Leave | Legally required | Talent, Leave and Engagement | Wave 1 | 2026-11-09 | 2026-11-20 | 2026-12-11 | 2027-01-08 | 2027-01-22 | 2027-01-29 |  | 2027-01-29 | Not started | Total Rewards (Benefits)
POL-39 | Right to Disconnect | Policy | Move | Legally required | HR Operations and Employee Lifecycle | Wave 1 | 2026-11-09 | 2026-11-20 | 2026-12-11 | 2027-01-08 | 2027-01-22 | 2027-01-29 |  | 2027-01-29 | Not started | HR Policy (People Ops)
POL-41 | Travel Safety & Restricted Travel | Policy | Move | Semiconductor-specific | HR Operations and Employee Lifecycle | Wave 1 | 2026-11-09 | 2026-11-20 | 2026-12-11 | 2027-01-08 | 2027-01-22 | 2027-01-29 |  | 2027-01-29 | Not started | Security (Travel Risk) with Trade Compliance
POL-46 | Employee Privacy & HR Data Protection | Policy | Data | Legally required | HR Data, Safety and Systems | Wave 1 | 2026-11-09 | 2026-11-20 | 2026-12-11 | 2027-01-08 | 2027-01-22 | 2027-01-29 |  | 2027-01-29 | Not started | Privacy Office with HR Operations (HRIS)
POL-47 | Electronic Monitoring & Acceptable Use | Policy | Data | Legally required | HR Data, Safety and Systems | Wave 1 | 2026-11-09 | 2026-11-20 | 2026-12-11 | 2027-01-08 | 2027-01-22 | 2027-01-29 |  | 2027-01-29 | Not started | Security (IT Security and Insider Risk) with the Privacy Office and HR
POL-48 | Confidential Information, IP & Inventions | Policy | Data | Semiconductor-specific | HR Data, Safety and Systems | Wave 1 | 2026-11-09 | 2026-11-20 | 2026-12-11 | 2027-01-08 | 2027-01-22 | 2027-01-29 |  | 2027-01-29 | Not started | Legal (IP and Employment) with Security (Insider Risk)
POL-49 | HR Records Retention | Policy | Data | Legally required | HR Data, Safety and Systems | Wave 1 | 2026-11-09 | 2026-11-20 | 2026-12-11 | 2027-01-08 | 2027-01-22 | 2027-01-29 |  | 2027-01-29 | Not started | HR Operations (People Ops) with Legal (Records Management)
POL-50 | AI in Employment Decisions | Policy | Data | Legally required | HR Data, Safety and Systems | Wave 1 | 2026-11-09 | 2026-11-20 | 2026-12-11 | 2027-01-08 | 2027-01-22 | 2027-01-29 |  | 2027-01-29 | Not started | HR Technology with Legal (Employment and Privacy) and HR Analytics
POL-51 | Health & Safety | Policy | Safety | Legally required | HR Data, Safety and Systems | Wave 1 | 2026-11-09 | 2026-11-20 | 2026-12-11 | 2027-01-08 | 2027-01-22 | 2027-01-29 |  | 2027-01-29 | Not started | EHS (Environment, Health & Safety)
POL-53 | Termination of Employment | Policy | Offboard | Legally required | HR Operations and Employee Lifecycle | Wave 1 | 2026-11-09 | 2026-11-20 | 2026-12-11 | 2027-01-08 | 2027-01-22 | 2027-01-29 |  | 2027-01-29 | Not started | Employee Relations with HR Business Partners
POL-54 | Severance & Reduction in Force | Policy | Offboard | Legally required | HR Operations and Employee Lifecycle | Wave 1 | 2026-11-09 | 2026-11-20 | 2026-12-11 | 2027-01-08 | 2027-01-22 | 2027-01-29 |  | 2027-01-29 | Not started | HR (Employee Relations and Total Rewards) with Legal
POL-55 | Return of Property & Post-Employment Obligations | Policy | Offboard | Semiconductor-specific | HR Operations and Employee Lifecycle | Wave 1 | 2026-11-09 | 2026-11-20 | 2026-12-11 | 2027-01-08 | 2027-01-22 | 2027-01-29 |  | 2027-01-29 | Not started | HR Operations (Offboarding) with Security and Legal
R-035 | Ontario pay equity maintenance | Program | Reward | Legally required | Total Rewards and Payroll | Wave 1 | 2026-11-09 | 2026-11-20 | 2026-12-11 | 2027-01-08 | 2027-01-22 | 2027-01-29 |  | 2027-01-29 | Not started | Total Rewards + Legal (Canada)
R-058 | India gratuity funding, actuarial valuation & nominations | Program | Benefits | Legally required | Total Rewards and Payroll | Wave 1 | 2026-11-09 | 2026-11-20 | 2026-12-11 | 2027-01-08 | 2027-01-22 | 2027-01-29 |  | 2027-01-29 | Not started | Total Rewards + Finance + Payroll (India)
R-060 | Taiwan Employee Welfare Committee & welfare fund | Committee | Benefits | Legally required | Total Rewards and Payroll | Wave 1 | 2026-11-09 | 2026-11-20 | 2026-12-11 | 2027-01-08 | 2027-01-22 | 2027-01-29 |  | 2027-01-29 | Not started | Taiwan HR + Finance
R-094 | California IIPP & indoor heat illness prevention plan | Program | Safety | Legally required | HR Data, Safety and Systems | Wave 1 | 2026-11-09 | 2026-11-20 | 2026-12-11 | 2027-01-08 | 2027-01-22 | 2027-01-29 |  | 2027-01-29 | Not started | EHS + Facilities (California)
R-095 | California Workplace Violence Prevention Plan: annual review, incident log & training | Program | Safety | Legally required | HR Data, Safety and Systems | Wave 1 | 2026-11-09 | 2026-11-20 | 2026-12-11 | 2027-01-08 | 2027-01-22 | 2027-01-29 |  | 2027-01-29 | Not started | EHS + Security + Employee Relations
R-DE-05 | Germany Interessenausgleich & Sozialplan | Committee | Offboard | Legally required | HR Operations and Employee Lifecycle | Wave 1 | 2026-11-09 | 2026-11-20 | 2026-12-11 | 2027-01-08 | 2027-01-22 | 2027-01-29 |  | 2027-01-29 | Not started | Employee Relations + Legal + Finance (Germany)
R-DE-20 | Germany employee invention (ArbnErfG) process | Program | Reward | Legally required | Total Rewards and Payroll | Wave 1 | 2026-11-09 | 2026-11-20 | 2026-12-11 | 2027-01-08 | 2027-01-22 | 2027-01-29 |  | 2027-01-29 | Not started | IP Legal + Engineering + Germany HR
R-USNC-06 | E-Verify program for NC new hires | Program | Onboard | Legally required | HR Operations and Employee Lifecycle | Wave 1 | 2026-11-09 | 2026-11-20 | 2026-12-11 | 2027-01-08 | 2027-01-22 | 2027-01-29 |  | 2027-01-29 | Not started | People Ops (I-9/E-Verify) + Employment Legal
CO-02 | Annual compensation review | Process | Reward | Legally required | Total Rewards and Payroll | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Total Rewards (process), HRBP (manager enablement and calibration), FP&A (budget), Payroll (load and reconciliation); Comp Committee approves officer pay and the equity pool
CO-07 | Executive compensation cycle | Process | Reward | Public-company driven | Total Rewards and Payroll | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Comp Committee (decisions), Total Rewards - Executive Compensation (process), Legal - Securities/Corporate Secretary (disclosure and filings), CHRO (management accountability)
EQ-01 | Equity grant administration | Process | Equity | Legally required | Total Rewards and Payroll | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Stock Admin (process), Total Rewards (guidelines and requests), Legal (plan, securities and country feasibility), Finance (ASC 718), Comp Committee (approval and delegation)
MV-02 | International assignment | Process | Move | Legally required | HR Operations and Employee Lifecycle | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Mobility (process), Finance/Tax (tax and PE), Immigration and Trade Compliance (gates), Payroll (home, host and shadow payroll)
OF-01 | Voluntary resignation & offboarding | Process | Offboard | Legally required | HR Operations and Employee Lifecycle | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | HRBP (process), People Ops (execution), Security with Legal (trade-secret triage)
OF-02 | Involuntary termination | Process | Offboard | Legally required | HR Operations and Employee Lifecycle | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | HRBP (process), Employee Relations (risk review and quality), Legal (approval for all non-US and high-risk US cases)
OF-03 | Reduction in force | Process | Offboard | Legally required | HR Operations and Employee Lifecycle | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | CHRO (accountable), HRBP (execution), Legal (privilege, thresholds, notices), FP&A/Finance (business case and restructuring accounting)
OF-07 | Exit survey & interview program | Process | Offboard | Legally required | HR Operations and Employee Lifecycle | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | HR Analytics (program and reporting), HRBP (interviews and actions), Employee Relations and Ethics & Compliance (allegation triage)
PL-02 | Requisition & position approval | Process | Plan | Legally required | Talent Acquisition | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | HRBP (process), FP&A (budget control), People Ops (position management), Trade Compliance (role classification)
POL-10 | Respectful Workplace & Anti-Bullying | Policy | Relations | Legally required | Governance, Ethics and Employee Relations | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | HR (Employee Relations) with EHS for psychological health and safety
POL-11 | Workplace Violence Prevention | Policy | Relations | Legally required | Governance, Ethics and Employee Relations | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Security (Corporate Security) with EHS; Employee Relations for employee-related threat assessment
POL-12 | Drug, Alcohol & Substance Use | Policy | Relations | Legally required | Governance, Ethics and Employee Relations | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | HR (Employee Relations) with EHS
POL-13 | Standards of Conduct & Corrective Action | Policy | Relations | Legally required | Governance, Ethics and Employee Relations | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | HR (Employee Relations)
POL-14 | Social Media & External Communications | Policy | Relations | Public-company driven | Governance, Ethics and Employee Relations | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Corporate Communications with Legal (Securities) and HR
POL-15 | Human Rights & Labor Standards | Policy | Relations | Semiconductor-specific | Governance, Ethics and Employee Relations | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Ethics & Compliance / ESG with HR (own operations) and Procurement (supply chain)
POL-21 | Probation & Confirmation | Policy | Recruit | Legally required | Talent Acquisition | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | HR Business Partners (process) with People Ops (tracking)
POL-45 | Mandatory Training & Policy Acknowledgment | Policy | Grow | Legally required | Talent, Leave and Engagement | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Learning & Development with Ethics & Compliance (policy governance)
POL-57 | Accessibility & Inclusion | Policy | Relations | Legally required | Governance, Ethics and Employee Relations | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | HR (Talent and Inclusion) with People Ops and Facilities
PY-01 | Payroll cycle: change control & close | Process | Pay | Legally required | Total Rewards and Payroll | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Payroll (process and control operation), Finance/Controller (SOX control owner and GL), People Ops (HRIS input quality)
R-003 | Background-check disclosures & adverse-action notices (FCRA, ICRAA, CA Fair Chance Act) | Notice | Recruit | Legally required | Talent Acquisition | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Talent Acquisition + Background-check vendor + Employment Legal
R-012 | Taiwan disability employment quota | Program | Recruit | Legally required | Talent Acquisition | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Taiwan HR + Talent Acquisition
R-015 | California new-hire notice pack | Notice | Onboard | Legally required | HR Operations and Employee Lifecycle | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | People Ops (California)
R-016 | Ontario new-hire information statement & 30-day document delivery | Notice | Onboard | Legally required | HR Operations and Employee Lifecycle | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | People Ops (Canada)
R-020 | Annual statutory rate & threshold update control | Control | Pay | Legally required | Total Rewards and Payroll | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Payroll + Total Rewards
R-021 | Form W-2/W-3, Forms 941/940 & OBBBA overtime reporting | Filing | Pay | Legally required | Total Rewards and Payroll | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Payroll + Tax
R-022 | California wage statement & meal/rest premium controls | Control | Pay | Legally required | Total Rewards and Payroll | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Payroll + Timekeeping admin
R-023 | Canada: CRA source-deduction remittances & T4/T4A slips | Filing | Pay | Legally required | Total Rewards and Payroll | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Payroll (Canada)
R-024 | India salary TDS: monthly deposit, Form 138 returns & Form 130 (formerly Form 16) | Filing | Pay | Legally required | Total Rewards and Payroll | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Payroll (India) + Tax
R-025 | India professional tax & Labour Welfare Fund | Filing | Pay | Legally required | Total Rewards and Payroll | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Payroll (India)
R-026 | India wage payment timing, wage slips & statutory bonus | Control | Pay | Legally required | Total Rewards and Payroll | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Payroll (India) + India HR Ops
R-027 | Taiwan withholding statements & NHI supplementary premium | Filing | Pay | Legally required | Total Rewards and Payroll | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Payroll (Taiwan)
R-044 | Designated-insider lists & quarterly blackout notices | Notice | Equity | Public-company driven | Total Rewards and Payroll | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Legal (Securities) + Stock Admin + HR Communications
R-054 | Group health plan participant notices (COBRA, Part D, CHIP, WHCRA, SBC) | Notice | Benefits | Legally required | Total Rewards and Payroll | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Benefits + Benefits admin platform
R-062 | FMLA notices & poster | Notice | Leave | Legally required | Talent, Leave and Engagement | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Leave administration (Benefits) + People Ops
R-064 | California leave notices (CFRA/PDL, victims' leave, lactation, PSL poster) | Notice | Leave | Legally required | Talent, Leave and Engagement | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | People Ops + Leave administration (California)
R-065 | India maternity benefit intimation & creche facility | Notice | Leave | Legally required | Talent, Leave and Engagement | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | India HR Ops + Benefits
R-069 | AODA employment standards program (accommodation plans, RTW, emergency info, training) | Program | Leave | Legally required | Talent, Leave and Engagement | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | People Ops (Canada) + L&D + Leave administration
R-080 | SOX 301 complaint procedures & global speak-up hotline | Program | Relations | Public-company driven | Governance, Ethics and Employee Relations | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Ethics & Compliance + Employee Relations + Audit Committee
R-082 | India POSH Internal Committee: constitution, display & annual report | Committee | Relations | Legally required | Governance, Ethics and Employee Relations | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | India HR + Internal Committee + Company Secretary
R-083 | India Grievance Redressal Committee | Committee | Relations | Legally required | Governance, Ethics and Employee Relations | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | India HR + Employee Relations
R-085 | India designated equal-opportunity officers & policies | Program | Relations | Legally required | Governance, Ethics and Employee Relations | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | India HR + Legal
R-087 | Taiwan labor-management meetings (quarterly) | Committee | Relations | Legally required | Governance, Ethics and Employee Relations | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Taiwan HR + Works Council/Union (employee representatives)
R-088 | Taiwan sexual-harassment & workplace-bullying prevention measures | Program | Relations | Legally required | Governance, Ethics and Employee Relations | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Taiwan HR + Employee Relations
R-091 | China anti-sexual harassment system | Program | Relations | Legally required | Governance, Ethics and Employee Relations | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | China HR + Employee Relations
R-096 | Lab chemical safety: HazCom 2024 update, Chemical Hygiene Plan & radiation/laser registrations | Program | Safety | Legally required | HR Data, Safety and Systems | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | EHS + Lab managers + Facilities
R-097 | Ontario OHS policy & violence/harassment programs: annual review & postings | Program | Safety | Legally required | HR Data, Safety and Systems | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | EHS + People Ops (Canada) + JHSC
R-098 | BC OHS program, bullying & harassment procedures, first aid & working alone | Program | Safety | Legally required | HR Data, Safety and Systems | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | EHS + People Ops (Canada) + JOHSC
R-099 | Canada joint health & safety committees | Committee | Safety | Legally required | HR Data, Safety and Systems | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | EHS + People Ops (Canada)
R-100 | Taiwan OSH management, health services & Art. 6(2) prevention plans | Program | Safety | Legally required | HR Data, Safety and Systems | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | EHS + Taiwan HR
R-101 | Statutory health examinations (Taiwan, China, India) | Program | Safety | Legally required | HR Data, Safety and Systems | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | EHS + local HR
R-102 | China work safety responsibility system & lab hazardous chemicals | Program | Safety | Legally required | HR Data, Safety and Systems | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | EHS + China HR + Facilities
R-105 | CCPA/CPRA employee & applicant privacy program (notice, rights, risk assessments, ADMT) | Program | Data | Legally required | HR Data, Safety and Systems | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Privacy + HR Ops + HR Analytics
R-108 | BC PIPA privacy officer & employee information practices | Program | Data | Legally required | HR Data, Safety and Systems | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Privacy + People Ops (Canada)
R-109 | India SPDI compliance & DPDP readiness (May 13, 2027) | Program | Data | Legally required | HR Data, Safety and Systems | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Privacy + India HR + IT Security
R-111 | Taiwan PDPA security maintenance & breach notification | Program | Data | Legally required | HR Data, Safety and Systems | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Privacy + IT Security + Taiwan HR
R-118 | Compensation committee charter, independence & advisor assessment | Committee | Governance | Public-company driven | Governance, Ethics and Employee Relations | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Total Rewards + Corporate Secretary + Legal
R-122 | Technology Control Plan & license-conditioned employee register | Program | Governance | Semiconductor-specific | Governance, Ethics and Employee Relations | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Trade Compliance + IT Security + Facilities + HR Ops
R-134 | Federal WARN & state mini-WARN notices (with disclosure timing) | Notice | Offboard | Legally required | HR Operations and Employee Lifecycle | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Employee Relations + Employment Legal + Legal (Securities) + Immigration
R-135 | Cal-WARN notices (SB 617 content) | Notice | Offboard | Legally required | HR Operations and Employee Lifecycle | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Employee Relations + Employment Legal (California)
R-136 | OWBPA group-termination disclosures | Notice | Offboard | Legally required | HR Operations and Employee Lifecycle | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Employment Legal + HR Analytics + Employee Relations
R-DE-10 | Germany BEM (occupational reintegration management) | Program | Leave | Legally required | Talent, Leave and Engagement | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Germany HR + Occupational Health
R-DE-15 | Germany occupational safety organisation & risk assessment | Committee | Safety | Legally required | HR Data, Safety and Systems | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | EHS + Germany HR + Facilities
R-DE-18 | Germany DPO, processing records & DPIAs | Program | Data | Legally required | HR Data, Safety and Systems | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Privacy + Germany HR + IT Security
R-IL-02 | Written notice of employment terms | Notice | Onboard | Legally required | HR Operations and Employee Lifecycle | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | HR Operations
R-IL-03 | Mandatory pension enrolment and Section 14 arrangement | Program | Benefits | Legally required | Total Rewards and Payroll | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Payroll + Benefits
R-IL-09 | Disability representation and responsible officer | Program | Recruit | Legally required | Talent Acquisition | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Talent Acquisition + HR / DEI
R-IL-15 | Occupational safety programme (plan, trustees, training) | Program | Safety | Legally required | HR Data, Safety and Systems | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | EHS + Site Operations
R-USCO-06 | Workplace posters and payday notice | Notice | Pay | Legally required | Total Rewards and Payroll | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | People Ops + Facilities
R-USCO-07 | HFWA paid sick leave program and notice | Program | Leave | Legally required | Talent, Leave and Engagement | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Leave team + Payroll
R-USNC-01 | Written wage notice at hire and wage-policy availability | Notice | Onboard | Legally required | HR Operations and Employee Lifecycle | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | People Ops + Payroll
R-USNC-02 | One-pay-period written notice of wage reductions | Notice | Pay | Legally required | Total Rewards and Payroll | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Payroll + Total Rewards + HRBPs
R-USNC-03 | Written forfeiture terms for vacation, bonuses and commissions | Notice | Pay | Legally required | Total Rewards and Payroll | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Total Rewards + People Ops
R-USTX-01 | Payday schedule & posted payday notice (Texas Payday Law) | Notice | Pay | Legally required | Total Rewards and Payroll | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Payroll + HR Operations
R-USTX-04 | Written PTO, sick and severance pay policy (payout terms) | Program | Leave | Legally required | Talent, Leave and Engagement | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Total Rewards + Employment Legal
R-USWA-03 | State paid sick leave and Seattle PSST program | Program | Leave | Legally required | Talent, Leave and Engagement | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Leave & Absence + Payroll + HR Ops
R-USWA-10 | Mini-WARN notices for closings and mass layoffs | Notice | Offboard | Legally required | HR Operations and Employee Lifecycle | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Employment Legal + HRBP + Payroll
R-USWA-14 | I-9 inspection notices to workers | Notice | Onboard | Legally required | HR Operations and Employee Lifecycle | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Immigration/I-9 Compliance + Employment Legal
R-USWA-17 | Seattle labor standards compliance | Program | Pay | Legally required | Total Rewards and Payroll | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | HR Ops + Payroll + Procurement
R-USWA-20 | Pregnancy accommodation and lactation program | Program | Leave | Legally required | Talent, Leave and Engagement | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Leave & Absence + Facilities
R-VN-10 | Vietnam salary scale, payroll table & bonus regulation | Notice | Reward | Legally required | Total Rewards and Payroll | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Total Rewards + Vietnam HR
TA-03 | Structured interview & selection | Process | Recruit | Legally required | Talent Acquisition | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Talent Acquisition (process), Hiring Manager (decision), Legal (AI tool governance), HR Analytics (adverse-impact monitoring)
TA-04 | Offer approval & extension | Process | Recruit | Legally required | Talent Acquisition | Wave 1 | 2026-11-16 | 2026-11-27 | 2026-12-18 | 2027-01-15 | 2027-01-29 | 2027-02-05 |  | 2027-02-05 | Not started | Talent Acquisition (process), Total Rewards (bands and equity guidelines), Legal (offer and contract templates)
ON-01 | Preboarding (accept to Day 1) | Process | Onboard | Legally required | HR Operations and Employee Lifecycle | Wave 1 | 2026-11-23 | 2026-12-04 | 2027-01-08 | 2027-01-22 | 2027-02-05 | 2027-02-12 |  | 2027-02-12 | Not started | People Ops (process), Recruiter (candidate relationship to Day 1), Trade Compliance (export clearance gate)
ON-04 | Day 1 to Day 90 onboarding & probation | Process | Onboard | Legally required | HR Operations and Employee Lifecycle | Wave 1 | 2026-11-23 | 2026-12-04 | 2027-01-08 | 2027-01-22 | 2027-02-05 | 2027-02-12 |  | 2027-02-12 | Not started | Manager (ramp and probation recommendation), HRBP (probation decision quality), People Ops (Day 1, tracking, letters), L&D (curriculum)
R-001 | Job-posting pay-range & salary-history controls (US states & California) | Control | Recruit | Legally required | Talent Acquisition | Wave 1 | 2026-11-23 | 2026-12-04 | 2027-01-08 | 2027-01-22 | 2027-02-05 | 2027-02-12 |  | 2027-02-12 | Not started | Talent Acquisition (Recruiting Ops) + Total Rewards
R-002 | Canadian job-posting rules: Ontario disclosures & 45-day outcome notice; BC pay range | Control | Recruit | Legally required | Talent Acquisition | Wave 1 | 2026-11-23 | 2026-12-04 | 2027-01-08 | 2027-01-22 | 2027-02-05 | 2027-02-12 |  | 2027-02-12 | Not started | Talent Acquisition (Canada) + People Ops
R-004 | Automated hiring & assessment tools: bias audits, notices and ADS records | Control | Recruit | Legally required | Talent Acquisition | Wave 1 | 2026-11-23 | 2026-12-04 | 2027-01-08 | 2027-01-22 | 2027-02-05 | 2027-02-12 |  | 2027-02-12 | Not started | TA Ops + HR Analytics + Employment Legal + Privacy
R-005 | Export-control role flag & nondiscriminatory U.S.-person question | Control | Recruit | Semiconductor-specific | Talent Acquisition | Wave 1 | 2026-11-23 | 2026-12-04 | 2027-01-08 | 2027-01-22 | 2027-02-05 | 2027-02-12 |  | 2027-02-12 | Not started | Trade Compliance + Talent Acquisition + Employment Legal
R-013 | Form I-9 & E-Verify: completion, reverification & annual internal audit | Control | Onboard | Legally required | HR Operations and Employee Lifecycle | Wave 1 | 2026-11-23 | 2026-12-04 | 2027-01-08 | 2027-01-22 | 2027-02-05 | 2027-02-12 |  | 2027-02-12 | Not started | People Ops + Immigration + Employment Legal
R-014 | State new-hire reporting, registrations & hire notices | Filing | Onboard | Legally required | HR Operations and Employee Lifecycle | Wave 1 | 2026-11-23 | 2026-12-04 | 2027-01-08 | 2027-01-22 | 2027-02-05 | 2027-02-12 |  | 2027-02-12 | Not started | Payroll + People Ops
R-018 | China written labor contract within one month | Control | Onboard | Legally required | HR Operations and Employee Lifecycle | Wave 1 | 2026-11-23 | 2026-12-04 | 2027-01-08 | 2027-01-22 | 2027-02-05 | 2027-02-12 |  | 2027-02-12 | Not started | China HR + Legal
R-019 | Confidentiality, invention assignment & clean-hire certification before access | Control | Onboard | Legally required | HR Operations and Employee Lifecycle | Wave 1 | 2026-11-23 | 2026-12-04 | 2027-01-08 | 2027-01-22 | 2027-02-05 | 2027-02-12 |  | 2027-02-12 | Not started | Legal (IP/Employment) + People Ops + Security
R-029 | China IIT monthly withholding & annual reconciliation support | Filing | Pay | Legally required | Total Rewards and Payroll | Wave 1 | 2026-11-23 | 2026-12-04 | 2027-01-08 | 2027-01-22 | 2027-02-05 | 2027-02-12 |  | 2027-02-12 | Not started | Payroll (China) + Tax
R-030 | China special working-hours system approval | Filing | Pay | Legally required | Total Rewards and Payroll | Wave 1 | 2026-11-23 | 2026-12-04 | 2027-01-08 | 2027-01-22 | 2027-02-05 | 2027-02-12 |  | 2027-02-12 | Not started | China HR + Legal
R-031 | SOX ICFR key controls: payroll & incentive accruals | Control | Pay | Public-company driven | Total Rewards and Payroll | Wave 1 | 2026-11-23 | 2026-12-04 | 2027-01-08 | 2027-01-22 | 2027-02-05 | 2027-02-12 |  | 2027-02-12 | Not started | Payroll + HR Ops + Finance (Controller) + Internal Audit
R-032 | California pay data report (CRD) | Filing | Reward | Legally required | Total Rewards and Payroll | Wave 1 | 2026-11-23 | 2026-12-04 | 2027-01-08 | 2027-01-22 | 2027-02-05 | 2027-02-12 |  | 2027-02-12 | Not started | HR Analytics + Total Rewards + Employment Legal
R-034 | BC pay transparency report (Nov 1) | Filing | Reward | Legally required | Total Rewards and Payroll | Wave 1 | 2026-11-23 | 2026-12-04 | 2027-01-08 | 2027-01-22 | 2027-02-05 | 2027-02-12 |  | 2027-02-12 | Not started | Total Rewards + HR Analytics (Canada)
R-036 | India 50% 'wages' structure test | Control | Reward | Legally required | Total Rewards and Payroll | Wave 1 | 2026-11-23 | 2026-12-04 | 2027-01-08 | 2027-01-22 | 2027-02-05 | 2027-02-12 |  | 2027-02-12 | Not started | Total Rewards + Payroll (India)
R-037 | Taiwan profit bonus & employee-compensation ratio | Control | Reward | Legally required | Total Rewards and Payroll | Wave 1 | 2026-11-23 | 2026-12-04 | 2027-01-08 | 2027-01-22 | 2027-02-05 | 2027-02-12 |  | 2027-02-12 | Not started | Total Rewards + Taiwan Finance/Legal
R-038 | Proxy CD&A, executive compensation tables & say-on-pay | Filing | Reward | Public-company driven | Total Rewards and Payroll | Wave 1 | 2026-11-23 | 2026-12-04 | 2027-01-08 | 2027-01-22 | 2027-02-05 | 2027-02-12 |  | 2027-02-12 | Not started | Total Rewards + Legal (Securities) + Corporate Secretary
R-039 | CEO pay ratio & pay versus performance | Filing | Reward | Public-company driven | Total Rewards and Payroll | Wave 1 | 2026-11-23 | 2026-12-04 | 2027-01-08 | 2027-01-22 | 2027-02-05 | 2027-02-12 |  | 2027-02-12 | Not started | Total Rewards + Global Payroll + Stock Admin + HR Analytics
R-040 | Executive tax-limit monitoring: 409A specified employees, 162(m) & 280G | Control | Reward | Public-company driven | Total Rewards and Payroll | Wave 1 | 2026-11-23 | 2026-12-04 | 2027-01-08 | 2027-01-22 | 2027-02-05 | 2027-02-12 |  | 2027-02-12 | Not started | Total Rewards + Tax + Employment Legal
R-041 | Export-compliance gates in sales incentive plans | Control | Reward | Semiconductor-specific | Total Rewards and Payroll | Wave 1 | 2026-11-23 | 2026-12-04 | 2027-01-08 | 2027-01-22 | 2027-02-05 | 2027-02-12 |  | 2027-02-12 | Not started | Total Rewards + Trade Compliance + Sales Ops
R-066 | India holiday list display & leave year-end processing | Notice | Leave | Legally required | Talent, Leave and Engagement | Wave 1 | 2026-11-23 | 2026-12-04 | 2027-01-08 | 2027-01-22 | 2027-02-05 | 2027-02-12 |  | 2027-02-12 | Not started | India HR Ops + Payroll
R-067 | Taiwan annual leave written statement & payout | Notice | Leave | Legally required | Talent, Leave and Engagement | Wave 1 | 2026-11-23 | 2026-12-04 | 2027-01-08 | 2027-01-22 | 2027-02-05 | 2027-02-12 |  | 2027-02-12 | Not started | Taiwan HR + Payroll
R-070 | California harassment prevention training | Training | Grow | Legally required | Talent, Leave and Engagement | Wave 1 | 2026-11-23 | 2026-12-04 | 2027-01-08 | 2027-01-22 | 2027-02-05 | 2027-02-12 |  | 2027-02-12 | Not started | L&D + Employee Relations
R-071 | Multi-state harassment training (NY, IL, CT, DE, ME) | Training | Grow | Legally required | Talent, Leave and Engagement | Wave 1 | 2026-11-23 | 2026-12-04 | 2027-01-08 | 2027-01-22 | 2027-02-05 | 2027-02-12 |  | 2027-02-12 | Not started | L&D + People Ops
R-072 | India POSH awareness & Internal Committee training | Training | Grow | Legally required | Talent, Leave and Engagement | Wave 1 | 2026-11-23 | 2026-12-04 | 2027-01-08 | 2027-01-22 | 2027-02-05 | 2027-02-12 |  | 2027-02-12 | Not started | India HR + L&D + Internal Committee
R-077 | Federal, state & California workplace postings | Notice | Relations | Legally required | Governance, Ethics and Employee Relations | Wave 1 | 2026-11-23 | 2026-12-04 | 2027-01-08 | 2027-01-22 | 2027-02-05 | 2027-02-12 |  | 2027-02-12 | Not started | People Ops + Facilities
R-106 | Ontario electronic monitoring policy | Notice | Data | Legally required | HR Data, Safety and Systems | Wave 1 | 2026-11-23 | 2026-12-04 | 2027-01-08 | 2027-01-22 | 2027-02-05 | 2027-02-12 |  | 2027-02-12 | Not started | Privacy + IT Security + People Ops (Canada)
R-127 | Conditional defense-work programs: ITAR registration & facility clearance (FSO, insider threat, FOCI) | Program | Governance | Semiconductor-specific | Governance, Ethics and Employee Relations | Wave 1 | 2026-11-23 | 2026-12-04 | 2027-01-08 | 2027-01-22 | 2027-02-05 | 2027-02-12 |  | 2027-02-12 | Not started | Trade Compliance (Empowered Official) + Security (FSO) + HR Ops
R-137 | California final pay & separation notice pack | Control | Offboard | Legally required | HR Operations and Employee Lifecycle | Wave 1 | 2026-11-23 | 2026-12-04 | 2027-01-08 | 2027-01-22 | 2027-02-05 | 2027-02-12 |  | 2027-02-12 | Not started | Payroll + People Ops + Benefits (California)
R-DE-02 | Germany works council information, consultation & co-determination | Committee | Relations | Legally required | Governance, Ethics and Employee Relations | Wave 1 | 2026-11-23 | 2026-12-04 | 2027-01-08 | 2027-01-22 | 2027-02-05 | 2027-02-12 |  | 2027-02-12 | Not started | Germany HR + Employee Relations + Legal
R-DE-06 | Germany HinSchG internal reporting office | Program | Governance | Legally required | Governance, Ethics and Employee Relations | Wave 1 | 2026-11-23 | 2026-12-04 | 2027-01-08 | 2027-01-22 | 2027-02-05 | 2027-02-12 |  | 2027-02-12 | Not started | Ethics & Compliance + Germany HR
R-DE-09 | Germany Schwerbehindertenvertretung & inclusion agreement | Committee | Relations | Legally required | Governance, Ethics and Employee Relations | Wave 1 | 2026-11-23 | 2026-12-04 | 2027-01-08 | 2027-01-22 | 2027-02-05 | 2027-02-12 |  | 2027-02-12 | Not started | Germany HR + Employee Relations
R-IL-01 | Sexual-harassment bylaw (takanon) and commissioner | Program | Relations | Legally required | Governance, Ethics and Employee Relations | Wave 1 | 2026-11-23 | 2026-12-04 | 2027-01-08 | 2027-01-22 | 2027-02-05 | 2027-02-12 |  | 2027-02-12 | Not started | HR / Employee Relations + Legal
R-IL-16 | Home Front Command emergency preparedness | Program | Safety | Legally required | HR Data, Safety and Systems | Wave 1 | 2026-11-23 | 2026-12-04 | 2027-01-08 | 2027-01-22 | 2027-02-05 | 2027-02-12 |  | 2027-02-12 | Not started | Security + EHS + HR
R-USNC-08 | Controlled substance testing compliance | Program | Safety | Legally required | HR Data, Safety and Systems | Wave 1 | 2026-11-23 | 2026-12-04 | 2027-01-08 | 2027-01-22 | 2027-02-05 | 2027-02-12 |  | 2027-02-12 | Not started | People Ops + Testing vendor + EHS
R-USNC-11 | Safety and health program and committees (experience modifier 1.5+) | Committee | Safety | Legally required | HR Data, Safety and Systems | Wave 1 | 2026-11-23 | 2026-12-04 | 2027-01-08 | 2027-01-22 | 2027-02-05 | 2027-02-12 |  | 2027-02-12 | Not started | EHS + Risk
R-USTX-19 | Severe-weather and grid-emergency plan | Program | Safety | Legally required | HR Data, Safety and Systems | Wave 1 | 2026-11-23 | 2026-12-04 | 2027-01-08 | 2027-01-22 | 2027-02-05 | 2027-02-12 |  | 2027-02-12 | Not started | EHS + Workplace Services + HR
R-USWA-08 | Accident Prevention Program | Program | Safety | Legally required | HR Data, Safety and Systems | Wave 1 | 2026-11-23 | 2026-12-04 | 2027-01-08 | 2027-01-22 | 2027-02-05 | 2027-02-12 |  | 2027-02-12 | Not started | EHS + Site Leads
R-USWA-09 | Safety committee or safety meetings | Committee | Safety | Legally required | HR Data, Safety and Systems | Wave 1 | 2026-11-23 | 2026-12-04 | 2027-01-08 | 2027-01-22 | 2027-02-05 | 2027-02-12 |  | 2027-02-12 | Not started | EHS + Site Leads
R-VN-02 | Vietnam workplace sexual harassment prevention (ILR section) | Program | Relations | Legally required | Governance, Ethics and Employee Relations | Wave 1 | 2026-11-23 | 2026-12-04 | 2027-01-08 | 2027-01-22 | 2027-02-05 | 2027-02-12 |  | 2027-02-12 | Not started | Vietnam HR + Employee Relations
R-VN-03 | Vietnam periodic workplace dialogue & annual employee conference | Committee | Relations | Legally required | Governance, Ethics and Employee Relations | Wave 1 | 2026-11-23 | 2026-12-04 | 2027-01-08 | 2027-01-22 | 2027-02-05 | 2027-02-12 |  | 2027-02-12 | Not started | Vietnam HR + Grassroots union
R-VN-15 | Vietnam OSH program: training, health checks, staffing & accident reporting | Program | Safety | Legally required | HR Data, Safety and Systems | Wave 1 | 2026-11-23 | 2026-12-04 | 2027-01-08 | 2027-01-22 | 2027-02-05 | 2027-02-12 |  | 2027-02-12 | Not started | EHS + Vietnam HR + Facilities
TA-06 | Export-control screening for new hires | Process | Recruit | Legally required | Talent Acquisition | Wave 1 | 2026-11-23 | 2026-12-04 | 2027-01-08 | 2027-01-22 | 2027-02-05 | 2027-02-12 |  | 2027-02-12 | Not started | Trade Compliance (determinations and Technology Control Plan), Talent Acquisition (workflow), Immigration (I-129 Part 6), IT (access gating)
DS-08 | Policy lifecycle governance | Process | Data | Legally required | HR Data, Safety and Systems | Wave 2 | 2027-02-15 | 2027-02-26 | 2027-03-19 | 2027-04-02 | 2027-04-16 | 2027-04-23 |  | 2027-04-23 | Not started | People Ops - HR Policy & Governance (process), domain policy owners (content), Legal (review), CHRO (approval)
R-006 | Deemed-export / deemed-reexport license determination before start or access | Control | Recruit | Semiconductor-specific | Talent Acquisition | Wave 2 | 2027-02-15 | 2027-02-26 | 2027-03-19 | 2027-04-02 | 2027-04-16 | 2027-04-23 |  | 2027-04-23 | Not started | Trade Compliance + Immigration + IT/Security
R-007 | Form I-129 Part 6 deemed-export certification | Filing | Recruit | Semiconductor-specific | Talent Acquisition | Wave 2 | 2027-02-15 | 2027-02-26 | 2027-03-19 | 2027-04-02 | 2027-04-16 | 2027-04-23 |  | 2027-04-23 | Not started | Immigration + Trade Compliance
R-008 | H-1B cap registration, LCA notice posting & public access file | Filing | Recruit | Legally required | Talent Acquisition | Wave 2 | 2027-02-15 | 2027-02-26 | 2027-03-19 | 2027-04-02 | 2027-04-16 | 2027-04-23 |  | 2027-04-23 | Not started | Immigration + outside immigration counsel + Total Rewards (wage level)
R-042 | Section 16 reporting: Form 4 within 2 business days (Forms 3/5, EDGAR Next) | Filing | Equity | Public-company driven | Total Rewards and Payroll | Wave 2 | 2027-02-15 | 2027-02-26 | 2027-03-19 | 2027-04-02 | 2027-04-16 | 2027-04-23 |  | 2027-04-23 | Not started | Legal (Securities) + Stock Admin + People Ops
R-043 | Insider trading disclosures: 10-K Exhibit 19, Item 408(a) & 408(b) | Filing | Equity | Public-company driven | Total Rewards and Payroll | Wave 2 | 2027-02-15 | 2027-02-26 | 2027-03-19 | 2027-04-02 | 2027-04-16 | 2027-04-23 |  | 2027-04-23 | Not started | Legal (Securities) + Stock Admin
R-045 | Clawback policy: 10-K Exhibit 97, Item 402(w) & executive acknowledgments | Filing | Equity | Public-company driven | Total Rewards and Payroll | Wave 2 | 2027-02-15 | 2027-02-26 | 2027-03-19 | 2027-04-02 | 2027-04-16 | 2027-04-23 |  | 2027-04-23 | Not started | Total Rewards + Legal + Finance (Controller)
R-046 | Equity grant calendar, Item 402(x) window control & Rule 16b-3 approvals | Control | Equity | Public-company driven | Total Rewards and Payroll | Wave 2 | 2027-02-15 | 2027-02-26 | 2027-03-19 | 2027-04-02 | 2027-04-16 | 2027-04-23 |  | 2027-04-23 | Not started | Stock Admin + Total Rewards + Legal (Securities)
R-047 | Equity plan shareholder approval, inducement grants & Form S-8 | Filing | Equity | Public-company driven | Total Rewards and Payroll | Wave 2 | 2027-02-15 | 2027-02-26 | 2027-03-19 | 2027-04-02 | 2027-04-16 | 2027-04-23 |  | 2027-04-23 | Not started | Total Rewards + Stock Admin + Legal (Securities)
R-048 | Forms 3921/3922 & ESPP/ISO statutory limit monitoring | Filing | Equity | Legally required | Total Rewards and Payroll | Wave 2 | 2027-02-15 | 2027-02-26 | 2027-03-19 | 2027-04-02 | 2027-04-16 | 2027-04-23 |  | 2027-04-23 | Not started | Stock Admin + Payroll + Tax
R-049 | SOX equity controls: ASC 718 & cap-table reconciliation | Control | Equity | Public-company driven | Total Rewards and Payroll | Wave 2 | 2027-02-15 | 2027-02-26 | 2027-03-19 | 2027-04-02 | 2027-04-16 | 2027-04-23 |  | 2027-04-23 | Not started | Stock Admin + Finance (Controller) + Internal Audit
R-073 | Code of conduct training, annual certification & waiver control | Training | Grow | Public-company driven | Talent, Leave and Engagement | Wave 2 | 2027-02-15 | 2027-02-26 | 2027-03-19 | 2027-04-02 | 2027-04-16 | 2027-04-23 |  | 2027-04-23 | Not started | Ethics & Compliance + L&D + Legal
R-074 | Insider trading & MNPI training | Training | Grow | Public-company driven | Talent, Leave and Engagement | Wave 2 | 2027-02-15 | 2027-02-26 | 2027-03-19 | 2027-04-02 | 2027-04-16 | 2027-04-23 |  | 2027-04-23 | Not started | Legal (Securities) + L&D + Stock Admin
R-075 | Export-control, TCP & travel-security training | Training | Grow | Semiconductor-specific | Talent, Leave and Engagement | Wave 2 | 2027-02-15 | 2027-02-26 | 2027-03-19 | 2027-04-02 | 2027-04-16 | 2027-04-23 |  | 2027-04-23 | Not started | Trade Compliance + L&D + Security
R-078 | SB 294 Workplace Know Your Rights notice (Feb 1) & emergency contact | Notice | Relations | Legally required | Governance, Ethics and Employee Relations | Wave 2 | 2027-02-15 | 2027-02-26 | 2027-03-19 | 2027-04-02 | 2027-04-16 | 2027-04-23 |  | 2027-04-23 | Not started | People Ops + Employee Relations (California)
R-079 | Ontario disconnecting-from-work written policy | Notice | Relations | Legally required | Governance, Ethics and Employee Relations | Wave 2 | 2027-02-15 | 2027-02-26 | 2027-03-19 | 2027-04-02 | 2027-04-16 | 2027-04-23 |  | 2027-04-23 | Not started | People Ops (Canada) + HR Policy
R-092 | OSHA injury logs: 300A posting & ITA e-submission | Filing | Safety | Legally required | HR Data, Safety and Systems | Wave 2 | 2027-02-15 | 2027-02-26 | 2027-03-19 | 2027-04-02 | 2027-04-16 | 2027-04-23 |  | 2027-04-23 | Not started | EHS + Facilities
R-138 | Canadian group termination notices (Ontario Form 1; BC notice to Minister) | Filing | Offboard | Legally required | HR Operations and Employee Lifecycle | Wave 2 | 2027-02-15 | 2027-02-26 | 2027-03-19 | 2027-04-02 | 2027-04-16 | 2027-04-23 |  | 2027-04-23 | Not started | Employee Relations + Legal (Canada)
R-139 | Record of Employment (ROE) within 5 days | Filing | Offboard | Legally required | HR Operations and Employee Lifecycle | Wave 2 | 2027-02-15 | 2027-02-26 | 2027-03-19 | 2027-04-02 | 2027-04-16 | 2027-04-23 |  | 2027-04-23 | Not started | Payroll (Canada)
R-140 | India retrenchment notice & Worker Re-skilling Fund deposit | Filing | Offboard | Legally required | HR Operations and Employee Lifecycle | Wave 2 | 2027-02-15 | 2027-02-26 | 2027-03-19 | 2027-04-02 | 2027-04-16 | 2027-04-23 |  | 2027-04-23 | Not started | Employee Relations (India) + Payroll + Legal
R-141 | India full & final settlement, gratuity & service certificate | Control | Offboard | Legally required | HR Operations and Employee Lifecycle | Wave 2 | 2027-02-15 | 2027-02-26 | 2027-03-19 | 2027-04-02 | 2027-04-16 | 2027-04-23 |  | 2027-04-23 | Not started | Payroll (India) + India HR Ops
R-DE-07 | Germany AGG complaint office & postings | Notice | Relations | Legally required | Governance, Ethics and Employee Relations | Wave 2 | 2027-02-15 | 2027-02-26 | 2027-03-19 | 2027-04-02 | 2027-04-16 | 2027-04-23 |  | 2027-04-23 | Not started | Germany HR + Legal
R-IL-13 | Employee privacy notice and monitoring policy | Notice | Data | Legally required | HR Data, Safety and Systems | Wave 2 | 2027-02-15 | 2027-02-26 | 2027-03-19 | 2027-04-02 | 2027-04-16 | 2027-04-23 |  | 2027-04-23 | Not started | Privacy Counsel + HR + IT Security
R-IL-14 | Whistleblower rights notice and anti-retaliation | Notice | Relations | Legally required | Governance, Ethics and Employee Relations | Wave 2 | 2027-02-15 | 2027-02-26 | 2027-03-19 | 2027-04-02 | 2027-04-16 | 2027-04-23 |  | 2027-04-23 | Not started | Ethics & Compliance + HR
R-USCO-15 | ADMT notices and adverse-decision explanations (from 1 Jan 2027) | Notice | Data | Legally required | HR Data, Safety and Systems | Wave 2 | 2027-02-15 | 2027-02-26 | 2027-03-19 | 2027-04-02 | 2027-04-16 | 2027-04-23 |  | 2027-04-23 | Not started | HR Analytics + TA Ops + Employment Legal + Privacy
R-USNC-12 | NC workplace postings | Notice | Governance | Legally required | Governance, Ethics and Employee Relations | Wave 2 | 2027-02-15 | 2027-02-26 | 2027-03-19 | 2027-04-02 | 2027-04-16 | 2027-04-23 |  | 2027-04-23 | Not started | People Ops + Facilities
R-USNC-19 | Firearm prohibition posting | Notice | Safety | Legally required | HR Data, Safety and Systems | Wave 2 | 2027-02-15 | 2027-02-26 | 2027-03-19 | 2027-04-02 | 2027-04-16 | 2027-04-23 |  | 2027-04-23 | Not started | Security + Facilities
ER-02 | Workplace investigation | Process | Relations | Legally required | Governance, Ethics and Employee Relations | Wave 2 | 2027-02-22 | 2027-03-05 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 |  | 2027-04-30 | Not started | Employee Relations (process & quality), Legal (privilege, external investigators, high-risk matters), HRBP & Manager (interim measures and outcomes)
R-009 | Foreign-national work authorization filings (Canada, India, Taiwan, China) | Filing | Recruit | Legally required | Talent Acquisition | Wave 2 | 2027-02-22 | 2027-03-05 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 |  | 2027-04-30 | Not started | Immigration/Global Mobility + local HR
R-010 | Government-official & related-person hiring screen | Control | Recruit | Public-company driven | Talent Acquisition | Wave 2 | 2027-02-22 | 2027-03-05 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 |  | 2027-04-30 | Not started | Ethics & Compliance + Talent Acquisition + Legal (Securities)
R-011 | India National Career Service vacancy notification | Filing | Recruit | Legally required | Talent Acquisition | Wave 2 | 2027-02-22 | 2027-03-05 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 |  | 2027-04-30 | Not started | Talent Acquisition (India) + India HR Ops
R-050 | SAFE Circular 7 equity plan registration & quarterly filings | Filing | Equity | Legally required | Total Rewards and Payroll | Wave 2 | 2027-02-22 | 2027-03-05 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 |  | 2027-04-30 | Not started | Stock Admin + China HR + Finance/Treasury
R-051 | Country equity tax & exchange-control compliance (Canada, India, Taiwan, China) | Control | Equity | Legally required | Total Rewards and Payroll | Wave 2 | 2027-02-22 | 2027-03-05 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 |  | 2027-04-30 | Not started | Stock Admin + Global Payroll + Tax + Legal
R-052 | ACA Forms 1094-C/1095-C | Filing | Benefits | Legally required | Total Rewards and Payroll | Wave 2 | 2027-02-22 | 2027-03-05 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 |  | 2027-04-30 | Not started | Benefits + Payroll + Benefits admin vendor
R-053 | Form 5500, PCORI fee & RxDC reporting | Filing | Benefits | Legally required | Total Rewards and Payroll | Wave 2 | 2027-02-22 | 2027-03-05 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 |  | 2027-04-30 | Not started | Benefits + Finance + plan auditor/TPA
R-056 | California benefit mandates: CalSavers, FTB coverage reporting, commuter benefit & SF HCSO | Filing | Benefits | Legally required | Total Rewards and Payroll | Wave 2 | 2027-02-22 | 2027-03-05 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 |  | 2027-04-30 | Not started | Benefits + Payroll (California)
R-057 | India EPF & ESI monthly contributions and returns | Filing | Benefits | Legally required | Total Rewards and Payroll | Wave 2 | 2027-02-22 | 2027-03-05 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 |  | 2027-04-30 | Not started | Payroll (India) + India HR Ops
R-059 | Taiwan day-one social insurance enrollment & labor pension reporting | Filing | Benefits | Legally required | Total Rewards and Payroll | Wave 2 | 2027-02-22 | 2027-03-05 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 |  | 2027-04-30 | Not started | Taiwan HR + Payroll
R-061 | China social insurance & housing fund: registration, contributions & annual base adjustment | Filing | Benefits | Legally required | Total Rewards and Payroll | Wave 2 | 2027-02-22 | 2027-03-05 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 |  | 2027-04-30 | Not started | China HR + Payroll/HR agency
R-076 | Anti-bribery training & certification | Training | Grow | Legally required | Talent, Leave and Engagement | Wave 2 | 2027-02-22 | 2027-03-05 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 |  | 2027-04-30 | Not started | Ethics & Compliance + L&D
R-084 | India standing orders / Karnataka IT exemption conditions & disciplinary reporting | Filing | Relations | Legally required | Governance, Ethics and Employee Relations | Wave 2 | 2027-02-22 | 2027-03-05 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 |  | 2027-04-30 | Not started | India HR + Employee Relations + Legal
R-086 | Taiwan work rules approval & posting (30+) | Filing | Relations | Legally required | Governance, Ethics and Employee Relations | Wave 2 | 2027-02-22 | 2027-03-05 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 |  | 2027-04-30 | Not started | Taiwan HR + Legal
R-089 | China employee handbook adopted via democratic procedure | Control | Relations | Legally required | Governance, Ethics and Employee Relations | Wave 2 | 2027-02-22 | 2027-03-05 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 |  | 2027-04-30 | Not started | China HR + Legal + Works Council/Union
R-090 | China trade union funds (2% of payroll) | Filing | Relations | Legally required | Governance, Ethics and Employee Relations | Wave 2 | 2027-02-22 | 2027-03-05 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 |  | 2027-04-30 | Not started | Payroll (China) + Finance
R-093 | Serious injury, fatality & work-injury reporting (all jurisdictions) | Filing | Safety | Legally required | HR Data, Safety and Systems | Wave 2 | 2027-02-22 | 2027-03-05 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 |  | 2027-04-30 | Not started | EHS + Leave administration + local HR
R-103 | India OSH Code establishment registration & lab factory licensing | Filing | Safety | Legally required | HR Data, Safety and Systems | Wave 2 | 2027-02-22 | 2027-03-05 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 |  | 2027-04-30 | Not started | India HR Ops + EHS + Facilities
R-104 | India night-shift, women's consent & 24x7 notification conditions | Control | Safety | Legally required | HR Data, Safety and Systems | Wave 2 | 2027-02-22 | 2027-03-05 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 |  | 2027-04-30 | Not started | India HR + Facilities/Security
R-107 | Biometric data controls (timeclocks, lab & cleanroom access) | Control | Data | Legally required | HR Data, Safety and Systems | Wave 2 | 2027-02-22 | 2027-03-05 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 |  | 2027-04-30 | Not started | Privacy + Security + Facilities
R-112 | DOJ Data Security Program diligence, audit & records | Control | Data | Semiconductor-specific | HR Data, Safety and Systems | Wave 2 | 2027-02-22 | 2027-03-05 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 |  | 2027-04-30 | Not started | Privacy/Security + Legal + HRIS + Global Payroll
R-114 | Confidential medical, I-9 & demographic data segregation | Control | Data | Legally required | HR Data, Safety and Systems | Wave 2 | 2027-02-22 | 2027-03-05 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 |  | 2027-04-30 | Not started | HR Ops + HRIS + Leave administration
R-115 | EEO-1 Component 1 report (rescission proposed) | Filing | Data | Legally required | HR Data, Safety and Systems | Wave 2 | 2027-02-22 | 2027-03-05 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 |  | 2027-04-30 | Not started | HR Analytics + Employment Legal
R-116 | 10-K human capital disclosure & metric evidence binder | Filing | Data | Public-company driven | HR Data, Safety and Systems | Wave 2 | 2027-02-22 | 2027-03-05 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 |  | 2027-04-30 | Not started | HR Analytics + HR Leadership + Legal (Securities) + Finance (SEC Reporting)
R-142 | Taiwan layoff notification (10 days) & mass redundancy plan (60 days) | Filing | Offboard | Legally required | HR Operations and Employee Lifecycle | Wave 2 | 2027-02-22 | 2027-03-05 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 |  | 2027-04-30 | Not started | Taiwan HR + Employee Relations + Legal
R-144 | China economic layoff report & union notification before unilateral termination | Filing | Offboard | Legally required | HR Operations and Employee Lifecycle | Wave 2 | 2027-02-22 | 2027-03-05 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 |  | 2027-04-30 | Not started | China HR + Legal + Works Council/Union
R-146 | Post-employment non-compete decisions (China, Taiwan, Washington) | Control | Offboard | Legally required | HR Operations and Employee Lifecycle | Wave 2 | 2027-02-22 | 2027-03-05 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 |  | 2027-04-30 | Not started | Employment Legal + HRBP + Payroll
R-147 | Sponsored-worker termination steps (H-1B, STEM OPT) | Filing | Offboard | Legally required | HR Operations and Employee Lifecycle | Wave 2 | 2027-02-22 | 2027-03-05 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 |  | 2027-04-30 | Not started | Immigration + Employee Relations
R-148 | Export-controlled access deprovisioning & license exit reporting | Control | Offboard | Semiconductor-specific | HR Operations and Employee Lifecycle | Wave 2 | 2027-02-22 | 2027-03-05 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 |  | 2027-04-30 | Not started | Trade Compliance + IT/Security + HR Ops
R-DE-03 | Germany works council hearing before every dismissal | Control | Offboard | Legally required | HR Operations and Employee Lifecycle | Wave 2 | 2027-02-22 | 2027-03-05 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 |  | 2027-04-30 | Not started | Employee Relations (Germany) + Legal
R-DE-04 | Germany mass-dismissal consultation & Agentur für Arbeit notification | Filing | Offboard | Legally required | HR Operations and Employee Lifecycle | Wave 2 | 2027-02-22 | 2027-03-05 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 |  | 2027-04-30 | Not started | Employee Relations + Legal (Germany)
R-DE-11 | Germany working-time recording & ArbZG limits | Control | Pay | Legally required | Total Rewards and Payroll | Wave 2 | 2027-02-22 | 2027-03-05 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 |  | 2027-04-30 | Not started | Germany HR + Payroll + Managers
R-DE-12 | Germany leave forfeiture notices | Notice | Leave | Legally required | Talent, Leave and Engagement | Wave 2 | 2027-02-22 | 2027-03-05 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 |  | 2027-04-30 | Not started | Germany HR Ops
R-DE-13 | Germany social insurance registration & contributions | Filing | Pay | Legally required | Total Rewards and Payroll | Wave 2 | 2027-02-22 | 2027-03-05 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 |  | 2027-04-30 | Not started | Payroll (Germany)
R-DE-14 | Germany wage-tax filings | Filing | Pay | Legally required | Total Rewards and Payroll | Wave 2 | 2027-02-22 | 2027-03-05 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 |  | 2027-04-30 | Not started | Payroll (Germany) + Tax
R-DE-17 | Germany maternity protection notification & assessment | Notice | Leave | Legally required | Talent, Leave and Engagement | Wave 2 | 2027-02-22 | 2027-03-05 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 |  | 2027-04-30 | Not started | Germany HR + EHS
R-IL-07 | Permit to dismiss pregnant or fertility-treatment employees | Filing | Offboard | Legally required | HR Operations and Employee Lifecycle | Wave 2 | 2027-02-22 | 2027-03-05 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 |  | 2027-04-30 | Not started | Employment Legal + HRBP
R-IL-18 | Foreign-expert work permits (B-1 / HIT) | Filing | Recruit | Legally required | Talent Acquisition | Wave 2 | 2027-02-22 | 2027-03-05 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 |  | 2027-04-30 | Not started | Global Mobility / Immigration
R-USCO-09 | Pregnancy accommodation notice | Notice | Leave | Legally required | Talent, Leave and Engagement | Wave 2 | 2027-02-22 | 2027-03-05 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 |  | 2027-04-30 | Not started | People Ops
R-USTX-08 | Texas workplace postings | Notice | Governance | Legally required | Governance, Ethics and Employee Relations | Wave 2 | 2027-02-22 | 2027-03-05 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 |  | 2027-04-30 | Not started | HR Operations
R-USWA-05 | PFML employee notices, job protection and health continuation | Notice | Leave | Legally required | Talent, Leave and Engagement | Wave 2 | 2027-02-22 | 2027-03-05 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 |  | 2027-04-30 | Not started | Leave & Absence + Benefits
R-USWA-11 | Noncompete compliance and void-noncompete notices | Notice | Governance | Legally required | Governance, Ethics and Employee Relations | Wave 2 | 2027-02-22 | 2027-03-05 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 |  | 2027-04-30 | Not started | Employment Legal + Stock Admin + HR Ops
R-USWA-15 | WA and Seattle workplace posters | Notice | Governance | Legally required | Governance, Ethics and Employee Relations | Wave 2 | 2027-02-22 | 2027-03-05 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 |  | 2027-04-30 | Not started | HR Ops + Facilities
LV-01 | Leave of absence | Process | Leave | Legally required | Talent, Leave and Engagement | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | Benefits - Leave & Accommodation team (process), leave vendor (US administration), Payroll (pay), HRBP (job protection and reinstatement)
LV-02 | Workplace accommodation | Process | Leave | Legally required | Talent, Leave and Engagement | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | Benefits - Leave & Accommodation team (process), HRBP (interactive process), Legal (denials and undue hardship), EHS (lab and reproductive-hazard assessments)
PD-02 | Performance review & calibration | Process | Grow | Legally required | Talent, Leave and Engagement | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | HRBP (process and calibration), People Ops (cycle administration), Dept Heads (rating approval), Legal/Employee Relations (high-risk review)
PD-03 | Performance improvement plan | Process | Grow | Legally required | Talent, Leave and Engagement | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | HRBP (process), Employee Relations (risk and quality), Legal (non-US and high-risk sign-off), Manager (execution)
PD-06 | Compliance training & policy attestation | Process | Grow | Legally required | Talent, Leave and Engagement | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | Ethics & Compliance (program owner), Legal (legal cadence and content), Trade Compliance (export modules), L&D and People Ops (delivery and LMS)
R-117 | SOX HRIS, payroll & equity-system access reviews and segregation of duties | Control | Data | Public-company driven | HR Data, Safety and Systems | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | HRIS + IT + Internal Audit
R-119 | SOX 302 HR sub-certifications & Disclosure Committee workforce briefing | Control | Governance | Public-company driven | Governance, Ethics and Employee Relations | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | CHRO + Payroll + Stock Admin + Finance (SEC Reporting)
R-120 | Form 8-K Item 5.02 officer & director change trigger | Filing | Governance | Public-company driven | Governance, Ethics and Employee Relations | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | Legal (Securities) + CHRO + Total Rewards
R-121 | Rule 21F-17 & protected-rights template review | Control | Governance | Public-company driven | Governance, Ethics and Employee Relations | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | Employment Legal + Employee Relations + HR Ops
R-123 | EAR 744.6 U.S.-person support review | Control | Governance | Semiconductor-specific | Governance, Ethics and Employee Relations | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | Trade Compliance + Employment Legal + Global Mobility
R-124 | Restricted-party screening of HR vendors, contractors & payees (Affiliates Rule returns Nov 10, 2026) | Control | Governance | Semiconductor-specific | Governance, Ethics and Employee Relations | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | Trade Compliance + Procurement + HR Ops
R-125 | Outbound-investment & foreign-talent-program questions in COI certification | Control | Governance | Semiconductor-specific | Governance, Ethics and Employee Relations | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | Legal + Ethics & Compliance + Security
R-126 | Taiwan national core key technology roster & cross-strait travel approvals | Control | Governance | Semiconductor-specific | Governance, Ethics and Employee Relations | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | Taiwan HR + Legal (Taiwan counsel) + Security
R-128 | RBA self-assessment, VAP audit evidence & human-rights due diligence | Filing | Governance | Semiconductor-specific | Governance, Ethics and Employee Relations | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | Supply Chain Sustainability + HR Ops + Legal/ESG
R-129 | Recruitment-fee & labor-agent due diligence (contract and dispatch labor) | Control | Governance | Semiconductor-specific | Governance, Ethics and Employee Relations | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | HR Ops + Supply Chain Sustainability + Procurement
R-DE-16 | Germany accident reporting & Berufsgenossenschaft annual report | Filing | Safety | Legally required | HR Data, Safety and Systems | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | EHS + Payroll (Germany)
R-DE-19 | EU AI Act HR controls (Germany) | Control | Data | Legally required | HR Data, Safety and Systems | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | Privacy + HR Technology + Legal
R-IL-04 | Attendance records and global-overtime reconciliation | Control | Pay | Legally required | Total Rewards and Payroll | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | Payroll + HR Operations + Employment Legal
R-IL-05 | Weekly-rest and holiday work permits | Filing | Pay | Legally required | Total Rewards and Payroll | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | HR Operations + Site Operations
R-IL-08 | Annual gender pay-gap report | Filing | Reward | Legally required | Total Rewards and Payroll | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | Total Rewards + People Analytics + Legal
R-IL-10 | Section 102 plan filing, trustee and ITA reporting | Filing | Equity | Legally required | Total Rewards and Payroll | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | Stock Administration + Tax + Israeli trustee
R-IL-11 | Payroll tax and NII filings (Forms 101/102/106/126/161) | Filing | Pay | Legally required | Total Rewards and Payroll | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | Payroll
R-IL-12 | HR database security documentation and incident reporting | Control | Data | Legally required | HR Data, Safety and Systems | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | HRIS + Information Security + Privacy Counsel
R-IL-17 | Extension-order entitlements (convalescence pay and travel) | Control | Pay | Legally required | Total Rewards and Payroll | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | Payroll + Total Rewards
R-USCO-01 | EPEWA job postings, promotional-opportunity and post-selection notices | Control | Recruit | Legally required | Talent Acquisition | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | Talent Acquisition (Recruiting Ops) + Total Rewards
R-USCO-03 | Initial application controls (JAFA and Chance to Compete) | Control | Recruit | Legally required | Talent Acquisition | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | Talent Acquisition Ops + Employment Legal
R-USCO-04 | Non-compete and non-solicit eligibility and separate notice | Control | Onboard | Legally required | HR Operations and Employee Lifecycle | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | Employment Legal + Total Rewards + TA
R-USCO-05 | Annual COMPS / PAY CALC / local minimum wage refresh | Control | Pay | Legally required | Total Rewards and Payroll | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | Total Rewards + Payroll + People Ops
R-USCO-08 | FAMLI premiums, wage reports and employee notice | Filing | Benefits | Legally required | Total Rewards and Payroll | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | Payroll + Benefits + Leave team
R-USCO-11 | Nondisclosure provisions compliance addendum | Control | Offboard | Legally required | HR Operations and Employee Lifecycle | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | Employment Legal
R-USCO-12 | Final pay and vacation payout control | Control | Offboard | Legally required | HR Operations and Employee Lifecycle | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | Payroll + HRBPs
R-USCO-13 | Biometric identifier policy and consent | Control | Data | Legally required | HR Data, Safety and Systems | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | Security + IT + Privacy + People Ops
R-USCO-14 | Personal data disposal policy and 30-day breach notice | Control | Data | Legally required | HR Data, Safety and Systems | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | Privacy + IT Security + People Ops
R-USCO-17 | Colorado SecureSavings exemption certification | Filing | Benefits | Legally required | Total Rewards and Payroll | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | Benefits
R-USCO-18 | Workers' comp designated providers and first report of injury | Filing | Safety | Legally required | HR Data, Safety and Systems | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | EHS + Leave team + Insurance
R-USNC-04 | Wage deduction authorization control | Control | Pay | Legally required | Total Rewards and Payroll | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | Payroll + Employment Legal
R-USNC-05 | Final pay by next regular payday | Control | Offboard | Legally required | HR Operations and Employee Lifecycle | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | Payroll + People Ops
R-USNC-09 | Workers' compensation coverage and Form 19 reporting | Filing | Safety | Legally required | HR Data, Safety and Systems | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | Benefits/Risk + EHS + Carrier
R-USNC-13 | New-hire reporting and state withholding registration | Filing | Onboard | Legally required | HR Operations and Employee Lifecycle | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | Payroll + People Ops
R-USNC-14 | NC withholding returns and annual reconciliation | Filing | Pay | Legally required | Total Rewards and Payroll | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | Payroll Tax
R-USNC-15 | DES quarterly unemployment reports | Filing | Pay | Legally required | Total Rewards and Payroll | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | Payroll Tax + People Ops
R-USNC-17 | Expunged-record and lawful-products screening control | Control | Recruit | Legally required | Talent Acquisition | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | Talent Acquisition + Background-check vendor
R-USNC-18 | Restrictive covenant execution and NC forum control | Control | Onboard | Semiconductor-specific | HR Operations and Employee Lifecycle | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | Employment Legal + Talent Acquisition
R-USTX-02 | Final-pay deadline control (6 days on discharge) | Control | Offboard | Legally required | HR Operations and Employee Lifecycle | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | Payroll + HRBPs
R-USTX-09 | New-hire reporting to the OAG | Filing | Onboard | Legally required | HR Operations and Employee Lifecycle | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | HR Operations / Payroll vendor
R-USTX-10 | Child support income withholding and termination notice | Control | Pay | Legally required | Total Rewards and Payroll | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | Payroll
R-USWA-01 | Job-posting pay range, benefits description and salary-history controls (EPOA) | Control | Recruit | Legally required | Talent Acquisition | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | Talent Acquisition Ops + Total Rewards + Employment Legal
R-USWA-12 | Fair chance background-check control | Control | Recruit | Legally required | Talent Acquisition | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | Talent Acquisition + Background-check vendor + Employment Legal
R-VN-16 | Vietnam annual leave schedule & holiday calendar | Notice | Leave | Legally required | Talent, Leave and Engagement | Wave 2 | 2027-03-01 | 2027-03-12 | 2027-04-02 | 2027-04-16 | 2027-04-30 | 2027-05-07 |  | 2027-05-07 | Not started | Vietnam HR Ops
MV-01 | Internal transfer & job change | Process | Move | Legally required | HR Operations and Employee Lifecycle | Wave 2 | 2027-03-08 | 2027-03-19 | 2027-04-09 | 2027-04-23 | 2027-05-07 | 2027-05-14 |  | 2027-05-14 | Not started | HRBP (process), receiving Manager (selection), People Ops (transaction)
PL-01 | Annual workforce & headcount plan | Process | Plan | Legally required | Talent Acquisition | Wave 2 | 2027-03-08 | 2027-03-19 | 2027-04-09 | 2027-04-23 | 2027-05-07 | 2027-05-14 |  | 2027-05-14 | Not started | FP&A (budget and model), HRBPs (workforce content), CHRO (sign-off with CFO)
PL-03 | Job architecture & leveling | Process | Plan | Legally required | Talent Acquisition | Wave 2 | 2027-03-08 | 2027-03-19 | 2027-04-09 | 2027-04-23 | 2027-05-07 | 2027-05-14 |  | 2027-05-14 | Not started | Total Rewards (architecture owner), HRBPs (application), HR Analytics (data), Legal (classification)
R-063 | State paid family/medical leave & sick-leave registrations and notices | Filing | Leave | Legally required | Talent, Leave and Engagement | Wave 2 | 2027-03-08 | 2027-03-19 | 2027-04-09 | 2027-04-23 | 2027-05-07 | 2027-05-14 |  | 2027-05-14 | Not started | Payroll + Leave administration
R-068 | China untaken annual leave settlement | Control | Leave | Legally required | Talent, Leave and Engagement | Wave 2 | 2027-03-08 | 2027-03-19 | 2027-04-09 | 2027-04-23 | 2027-05-07 | 2027-05-14 |  | 2027-05-14 | Not started | China HR + Payroll
R-130 | Canada forced & child labour supply-chain report (May 31) | Filing | Governance | Legally required | Governance, Ethics and Employee Relations | Wave 2 | 2027-03-08 | 2027-03-19 | 2027-04-09 | 2027-04-23 | 2027-05-07 | 2027-05-14 |  | 2027-05-14 | Not started | Legal (Canada) + Supply Chain Compliance + HR
R-131 | Federal contractor & DEI compliance (AAPs, VETS-4212, EO 14173 certification, statement review) | Filing | Governance | Legally required | Governance, Ethics and Employee Relations | Wave 2 | 2027-03-08 | 2027-03-19 | 2027-04-09 | 2027-04-23 | 2027-05-07 | 2027-05-14 |  | 2027-05-14 | Not started | Employment Legal + HR Analytics + Talent Acquisition
R-132 | AODA accessibility compliance report | Filing | Governance | Legally required | Governance, Ethics and Employee Relations | Wave 2 | 2027-03-08 | 2027-03-19 | 2027-04-09 | 2027-04-23 | 2027-05-07 | 2027-05-14 |  | 2027-05-14 | Not started | People Ops (Canada) + Legal + Web/IT
R-133 | India annual labour returns & electronic statutory registers | Filing | Governance | Legally required | Governance, Ethics and Employee Relations | Wave 2 | 2027-03-08 | 2027-03-19 | 2027-04-09 | 2027-04-23 | 2027-05-07 | 2027-05-14 |  | 2027-05-14 | Not started | India HR Ops + Payroll
R-DE-08 | Germany severely disabled employment report & Ausgleichsabgabe | Filing | Governance | Legally required | Governance, Ethics and Employee Relations | Wave 2 | 2027-03-08 | 2027-03-19 | 2027-04-09 | 2027-04-23 | 2027-05-07 | 2027-05-14 |  | 2027-05-14 | Not started | Germany HR Ops + Payroll
R-IL-06 | Reservist protection tracker and NII reimbursement | Control | Leave | Legally required | Talent, Leave and Engagement | Wave 2 | 2027-03-08 | 2027-03-19 | 2027-04-09 | 2027-04-23 | 2027-05-07 | 2027-05-14 |  | 2027-05-14 | Not started | HR Operations + Payroll + Employment Legal
R-USNC-16 | Personal information breach notification and SSN controls | Control | Data | Legally required | HR Data, Safety and Systems | Wave 2 | 2027-03-08 | 2027-03-19 | 2027-04-09 | 2027-04-23 | 2027-05-07 | 2027-05-14 |  | 2027-05-14 | Not started | Privacy Office + Security + HR Ops
R-USTX-05 | Workers' comp coverage notices & non-subscriber DWC Form-005 | Filing | Safety | Legally required | HR Data, Safety and Systems | Wave 2 | 2027-03-08 | 2027-03-19 | 2027-04-09 | 2027-04-23 | 2027-05-07 | 2027-05-14 |  | 2027-05-14 | Not started | Risk Management + HR Operations
R-USTX-06 | Workplace injury reports to carrier or TDI-DWC | Filing | Safety | Legally required | HR Data, Safety and Systems | Wave 2 | 2027-03-08 | 2027-03-19 | 2027-04-09 | 2027-04-23 | 2027-05-07 | 2027-05-14 |  | 2027-05-14 | Not started | EHS + Risk Management
R-USTX-11 | TWC unemployment tax reports and claim responses | Filing | Pay | Legally required | Total Rewards and Payroll | Wave 2 | 2027-03-08 | 2027-03-19 | 2027-04-09 | 2027-04-23 | 2027-05-07 | 2027-05-14 |  | 2027-05-14 | Not started | Payroll + HR Operations
R-USTX-12 | Biometric notice, consent and destruction (CUBI) | Control | Data | Legally required | HR Data, Safety and Systems | Wave 2 | 2027-03-08 | 2027-03-19 | 2027-04-09 | 2027-04-23 | 2027-05-07 | 2027-05-14 |  | 2027-05-14 | Not started | Security + Privacy + HR Operations
R-USTX-14 | Data breach notification (60 days / AG 30 days) | Control | Data | Legally required | HR Data, Safety and Systems | Wave 2 | 2027-03-08 | 2027-03-19 | 2027-04-09 | 2027-04-23 | 2027-05-07 | 2027-05-14 |  | 2027-05-14 | Not started | Privacy + Security + Legal
R-USWA-02 | Exempt salary floor and computer-professional rate review | Control | Pay | Legally required | Total Rewards and Payroll | Wave 2 | 2027-03-08 | 2027-03-19 | 2027-04-09 | 2027-04-23 | 2027-05-07 | 2027-05-14 |  | 2027-05-14 | Not started | Total Rewards + Payroll + Employment Legal
R-USWA-04 | PFML premiums and quarterly ESD reports | Filing | Benefits | Legally required | Total Rewards and Payroll | Wave 2 | 2027-03-08 | 2027-03-19 | 2027-04-09 | 2027-04-23 | 2027-05-07 | 2027-05-14 |  | 2027-05-14 | Not started | Payroll + Benefits
R-USWA-06 | WA Cares premium and exemption control | Control | Benefits | Legally required | Total Rewards and Payroll | Wave 2 | 2027-03-08 | 2027-03-19 | 2027-04-09 | 2027-04-23 | 2027-05-07 | 2027-05-14 |  | 2027-05-14 | Not started | Payroll + Global Mobility/Immigration
R-USWA-16 | Seattle payroll expense tax and Social Housing Tax filings | Filing | Pay | Legally required | Total Rewards and Payroll | Wave 2 | 2027-03-08 | 2027-03-19 | 2027-04-09 | 2027-04-23 | 2027-05-07 | 2027-05-14 |  | 2027-05-14 | Not started | Tax + Payroll + Stock Admin
R-VN-05 | Vietnam SI, HI & UI registration and monthly contributions | Filing | Benefits | Legally required | Total Rewards and Payroll | Wave 2 | 2027-03-08 | 2027-03-19 | 2027-04-09 | 2027-04-23 | 2027-05-07 | 2027-05-14 |  | 2027-05-14 | Not started | Payroll (Vietnam) + Vietnam HR Ops
R-VN-08 | Vietnam work permits & exemption notifications | Filing | Recruit | Legally required | Talent Acquisition | Wave 2 | 2027-03-08 | 2027-03-19 | 2027-04-09 | 2027-04-23 | 2027-05-07 | 2027-05-14 |  | 2027-05-14 | Not started | Immigration + Vietnam HR
R-VN-11 | Vietnam labour-use plan & 30-day restructuring notice | Filing | Offboard | Legally required | HR Operations and Employee Lifecycle | Wave 2 | 2027-03-08 | 2027-03-19 | 2027-04-09 | 2027-04-23 | 2027-05-07 | 2027-05-14 |  | 2027-05-14 | Not started | Vietnam HR + Legal + Employee Relations
R-VN-12 | Vietnam final settlement within 14 working days & SI closure | Control | Offboard | Legally required | HR Operations and Employee Lifecycle | Wave 2 | 2027-03-08 | 2027-03-19 | 2027-04-09 | 2027-04-23 | 2027-05-07 | 2027-05-14 |  | 2027-05-14 | Not started | Payroll (Vietnam) + Vietnam HR Ops
R-VN-18 | Vietnam labour contract form, term tracking & e-contract upload | Control | Onboard | Legally required | HR Operations and Employee Lifecycle | Wave 2 | 2027-03-08 | 2027-03-19 | 2027-04-09 | 2027-04-23 | 2027-05-07 | 2027-05-14 |  | 2027-05-14 | Not started | Vietnam HR Ops
BN-01 | New-hire benefits enrollment | Process | Benefits | Legally required | Total Rewards and Payroll | Wave 3 | 2027-05-17 | 2027-05-28 | 2027-06-18 | 2027-07-02 | 2027-07-16 | 2027-07-23 |  | 2027-07-23 | Not started | Benefits (process), Total Rewards (plan design), Payroll (deductions and statutory remittances)
BN-02 | Annual open enrollment | Process | Benefits | Legally required | Total Rewards and Payroll | Wave 3 | 2027-05-17 | 2027-05-28 | 2027-06-18 | 2027-07-02 | 2027-07-16 | 2027-07-23 |  | 2027-07-23 | Not started | Benefits (process), Total Rewards (plan design and contributions), Payroll (deduction cut-over)
BN-03 | Qualifying life events | Process | Benefits | Legally required | Total Rewards and Payroll | Wave 3 | 2027-05-17 | 2027-05-28 | 2027-06-18 | 2027-07-02 | 2027-07-16 | 2027-07-23 |  | 2027-07-23 | Not started | Benefits (process), benefits administration vendor (US processing), People Ops (non-US dependant and nomination records)
MV-03 | Permanent cross-border transfer | Process | Move | Legally required | HR Operations and Employee Lifecycle | Wave 3 | 2027-05-17 | 2027-05-28 | 2027-06-18 | 2027-07-02 | 2027-07-16 | 2027-07-23 |  | 2027-07-23 | Not started | Mobility (process), Legal (structure and documents), Stock Admin (equity continuity), Payroll (home exit and host set-up)
MV-04 | Remote work & work-location change | Process | Move | Legally required | HR Operations and Employee Lifecycle | Wave 3 | 2027-05-17 | 2027-05-28 | 2027-06-18 | 2027-07-02 | 2027-07-16 | 2027-07-23 |  | 2027-07-23 | Not started | HRBP (approval process), Payroll (registration), Trade Compliance and IT/Security (location controls)
MV-05 | Status & classification change | Process | Move | Legally required | HR Operations and Employee Lifecycle | Wave 3 | 2027-05-17 | 2027-05-28 | 2027-06-18 | 2027-07-02 | 2027-07-16 | 2027-07-23 |  | 2027-07-23 | Not started | Total Rewards (classification analysis), Legal (sign-off and remediation), People Ops and Payroll (implementation)
PL-04 | Organization design change | Process | Plan | Legally required | Talent Acquisition | Wave 3 | 2027-05-17 | 2027-05-28 | 2027-06-18 | 2027-07-02 | 2027-07-16 | 2027-07-23 |  | 2027-07-23 | Not started | HRBP (process), Dept Head (design), Legal and Employee Relations (consultation and risk)
PL-05 | Contingent workforce engagement | Process | Plan | Legally required | Talent Acquisition | Wave 3 | 2027-05-17 | 2027-05-28 | 2027-06-18 | 2027-07-02 | 2027-07-16 | 2027-07-23 |  | 2027-07-23 | Not started | People Ops (process and contingent register), Legal (classification), Trade Compliance (screening and technology access)
R-IL-20 | Union-organizing neutrality protocol | Control | Relations | Legally required | Governance, Ethics and Employee Relations | Wave 3 | 2027-05-17 | 2027-05-28 | 2027-06-18 | 2027-07-02 | 2027-07-16 | 2027-07-23 |  | 2027-07-23 | Not started | Employment Legal + HR Leadership
R-USCO-16 | State EEO-1 demographic filing (from 2027) | Filing | Governance | Legally required | Governance, Ethics and Employee Relations | Wave 3 | 2027-05-17 | 2027-05-28 | 2027-06-18 | 2027-07-02 | 2027-07-16 | 2027-07-23 |  | 2027-07-23 | Not started | HR Analytics + Employment Legal
R-USNC-07 | REDA retaliation pre-action review | Control | Relations | Legally required | Governance, Ethics and Employee Relations | Wave 3 | 2027-05-17 | 2027-05-28 | 2027-06-18 | 2027-07-02 | 2027-07-16 | 2027-07-23 |  | 2027-07-23 | Not started | Employment Legal + HRBPs
R-USTX-15 | Firearms-in-parking-lot and weapons policy control | Control | Safety | Legally required | HR Data, Safety and Systems | Wave 3 | 2027-05-17 | 2027-05-28 | 2027-06-18 | 2027-07-02 | 2027-07-16 | 2027-07-23 |  | 2027-07-23 | Not started | Security + Employment Legal
R-USTX-16 | Sexual-harassment complaint response standard (1+ employees) | Control | Relations | Legally required | Governance, Ethics and Employee Relations | Wave 3 | 2027-05-17 | 2027-05-28 | 2027-06-18 | 2027-07-02 | 2027-07-16 | 2027-07-23 |  | 2027-07-23 | Not started | Employee Relations + Employment Legal
R-USTX-17 | Jury, voting, state military and evacuation leave control | Control | Leave | Legally required | Talent, Leave and Engagement | Wave 3 | 2027-05-17 | 2027-05-28 | 2027-06-18 | 2027-07-02 | 2027-07-16 | 2027-07-23 |  | 2027-07-23 | Not started | HR Operations + Leave team
R-USWA-07 | L&I workers' comp account and quarterly hours report | Filing | Safety | Legally required | HR Data, Safety and Systems | Wave 3 | 2027-05-17 | 2027-05-28 | 2027-06-18 | 2027-07-02 | 2027-07-16 | 2027-07-23 |  | 2027-07-23 | Not started | Payroll + EHS + Risk Management
R-VN-07 | Vietnam PIT withholding, returns & annual finalization | Filing | Pay | Legally required | Total Rewards and Payroll | Wave 3 | 2027-05-17 | 2027-05-28 | 2027-06-18 | 2027-07-02 | 2027-07-16 | 2027-07-23 |  | 2027-07-23 | Not started | Payroll (Vietnam) + Tax
R-VN-09 | Vietnam overtime consent, caps & 300-hour notification | Control | Pay | Legally required | Total Rewards and Payroll | Wave 3 | 2027-05-17 | 2027-05-28 | 2027-06-18 | 2027-07-02 | 2027-07-16 | 2027-07-23 |  | 2027-07-23 | Not started | Vietnam HR + Payroll + Engineering managers
R-VN-13 | Vietnam PDPL impact assessments (DPIA & TIA) with the Ministry of Public Security | Filing | Data | Legally required | HR Data, Safety and Systems | Wave 3 | 2027-05-17 | 2027-05-28 | 2027-06-18 | 2027-07-02 | 2027-07-16 | 2027-07-23 |  | 2027-07-23 | Not started | Privacy + Vietnam HR + Legal
R-VN-19 | Vietnam task-completion criteria regulation | Control | Grow | Legally required | Talent, Leave and Engagement | Wave 3 | 2027-05-17 | 2027-05-28 | 2027-06-18 | 2027-07-02 | 2027-07-16 | 2027-07-23 |  | 2027-07-23 | Not started | Vietnam HR + Employee Relations
BN-04 | Retirement plan governance | Process | Benefits | Legally required | Total Rewards and Payroll | Wave 3 | 2027-05-24 | 2027-06-04 | 2027-06-25 | 2027-07-09 | 2027-07-23 | 2027-07-30 |  | 2027-07-30 | Not started | Retirement plan committee (fiduciary, chaired by the CFO), Total Rewards (plan sponsor administration), Benefits (non-US plans)
BN-05 | Global benefits renewal & vendor management | Process | Benefits | Legally required | Total Rewards and Payroll | Wave 3 | 2027-05-24 | 2027-06-04 | 2027-06-25 | 2027-07-09 | 2027-07-23 | 2027-07-30 |  | 2027-07-30 | Not started | Benefits (process), Total Rewards (strategy and decision), Legal and Security (contract and data terms), Finance (budget)
BN-06 | Benefits continuation (COBRA) | Process | Benefits | Legally required | Total Rewards and Payroll | Wave 3 | 2027-05-24 | 2027-06-04 | 2027-06-25 | 2027-07-09 | 2027-07-23 | 2027-07-30 |  | 2027-07-30 | Not started | Benefits (process), COBRA administrator (notices and administration), Payroll (subsidy funding), People Ops (event data)
CO-01 | Salary structures & market pricing | Process | Reward | Legally required | Total Rewards and Payroll | Wave 3 | 2027-05-24 | 2027-06-04 | 2027-06-25 | 2027-07-09 | 2027-07-23 | 2027-07-30 |  | 2027-07-30 | Not started | Total Rewards (process and ranges), HR Analytics (survey data), Legal (pay-transparency and antitrust review)
CO-03 | Annual bonus / variable pay | Process | Reward | Legally required | Total Rewards and Payroll | Wave 3 | 2027-05-24 | 2027-06-04 | 2027-06-25 | 2027-07-09 | 2027-07-23 | 2027-07-30 |  | 2027-07-30 | Not started | Total Rewards (design and calculation), Finance (accrual and funding certification), Comp Committee (plan approval and officer payouts)
CO-04 | Sales incentive compensation | Process | Reward | Legally required | Total Rewards and Payroll | Wave 3 | 2027-05-24 | 2027-06-04 | 2027-06-25 | 2027-07-09 | 2027-07-23 | 2027-07-30 |  | 2027-07-30 | Not started | Total Rewards - Sales Compensation (design and administration), Sales leadership (quotas), Finance (calculation review and accounting), Trade Compliance (order gate)
CO-05 | Off-cycle adjustments & counteroffers | Process | Reward | Legally required | Total Rewards and Payroll | Wave 3 | 2027-05-24 | 2027-06-04 | 2027-06-25 | 2027-07-09 | 2027-07-23 | 2027-07-30 |  | 2027-07-30 | Not started | HRBP (process and flight-risk judgement), Total Rewards (pricing), Dept Head and CHRO (approval authority)
CO-06 | Pay equity audit & remediation | Process | Reward | Legally required | Total Rewards and Payroll | Wave 3 | 2027-05-24 | 2027-06-04 | 2027-06-25 | 2027-07-09 | 2027-07-23 | 2027-07-30 |  | 2027-07-30 | Not started | Legal (privilege, scope and advice), HR Analytics (analysis), Total Rewards (remediation), CHRO (budget approval)
DS-01 | Employee data changes & data quality | Process | Data | Legally required | HR Data, Safety and Systems | Wave 3 | 2027-05-24 | 2027-06-04 | 2027-06-25 | 2027-07-09 | 2027-07-23 | 2027-07-30 |  | 2027-07-30 | Not started | People Ops (HRIS data steward), Payroll (payroll data), HR Analytics (data-quality reporting)
DS-02 | HR data subject requests | Process | Data | Legally required | HR Data, Safety and Systems | Wave 3 | 2027-05-24 | 2027-06-04 | 2027-06-25 | 2027-07-09 | 2027-07-23 | 2027-07-30 |  | 2027-07-30 | Not started | People Ops (HR privacy desk), Legal / Privacy (exemptions & review)
DS-03 | Records retention & destruction | Process | Data | Legally required | HR Data, Safety and Systems | Wave 3 | 2027-05-24 | 2027-06-04 | 2027-06-25 | 2027-07-09 | 2027-07-23 | 2027-07-30 |  | 2027-07-30 | Not started | People Ops (schedule owner), Legal (legal review & holds), IT (system purges)
DS-04 | HRIS access & segregation of duties | Process | Data | Legally required | HR Data, Safety and Systems | Wave 3 | 2027-05-24 | 2027-06-04 | 2027-06-25 | 2027-07-09 | 2027-07-23 | 2027-07-30 |  | 2027-07-30 | Not started | People Ops (HRIS role owner), IT (identity & access), Payroll (payroll-system roles), Finance / Internal Audit (SOX testing)
DS-05 | Human capital reporting & disclosure | Process | Data | Legally required | HR Data, Safety and Systems | Wave 3 | 2027-05-24 | 2027-06-04 | 2027-06-25 | 2027-07-09 | 2027-07-23 | 2027-07-30 |  | 2027-07-30 | Not started | HR Analytics (metrics & lineage), CHRO (sub-certification), Legal (Securities) and Finance (SEC Reporting) (disclosure)
EN-01 | Engagement survey & action planning | Process | Engage | Legally required | Talent, Leave and Engagement | Wave 3 | 2027-05-24 | 2027-06-04 | 2027-06-25 | 2027-07-09 | 2027-07-23 | 2027-07-30 |  | 2027-07-30 | Not started | HR Analytics (program), HRBPs (action planning), Legal (privacy and labor review)
EN-02 | Recognition & service awards | Process | Engage | Legally required | Talent, Leave and Engagement | Wave 3 | 2027-05-24 | 2027-06-04 | 2027-06-25 | 2027-07-09 | 2027-07-23 | 2027-07-30 |  | 2027-07-30 | Not started | People Ops (program administration), Total Rewards (design and budget), Payroll (tax), Ethics & Compliance (anti-bribery guardrails)
EN-03 | Stay interviews & listening | Process | Engage | Legally required | Talent, Leave and Engagement | Wave 3 | 2027-05-24 | 2027-06-04 | 2027-06-25 | 2027-07-09 | 2027-07-23 | 2027-07-30 |  | 2027-07-30 | Not started | HRBP (program), Managers (conduct interviews), HR Analytics (theme analysis)
ER-01 | Speak-up intake & triage | Process | Relations | Legally required | Governance, Ethics and Employee Relations | Wave 3 | 2027-05-24 | 2027-06-04 | 2027-06-25 | 2027-07-09 | 2027-07-23 | 2027-07-30 |  | 2027-07-30 | Not started | Ethics & Compliance (intake & triage), Employee Relations (HR-conduct matters), Legal (privilege & escalation)
ER-03 | Harassment complaints (statutory committees) | Process | Relations | Legally required | Governance, Ethics and Employee Relations | Wave 3 | 2027-05-24 | 2027-06-04 | 2027-06-25 | 2027-07-09 | 2027-07-23 | 2027-07-30 |  | 2027-07-30 | Not started | Employee Relations (process), country HR leads (committee administration), Legal (statutory notifications & filings)
LV-03 | Return to work | Process | Leave | Legally required | Talent, Leave and Engagement | Wave 3 | 2027-05-24 | 2027-06-04 | 2027-06-25 | 2027-07-09 | 2027-07-23 | 2027-07-30 |  | 2027-07-30 | Not started | Benefits - Leave & Accommodation team (process), HRBP (reinstatement), Manager (reboarding)
MV-06 | Immigration maintenance & green cards | Process | Move | Legally required | HR Operations and Employee Lifecycle | Wave 3 | 2027-05-24 | 2027-06-04 | 2027-06-25 | 2027-07-09 | 2027-07-23 | 2027-07-30 |  | 2027-07-30 | Not started | Immigration (program owner), outside immigration counsel (filings), HRBP (sponsorship decisions)
OF-04 | Separation agreements & releases | Process | Offboard | Legally required | HR Operations and Employee Lifecycle | Wave 3 | 2027-05-24 | 2027-06-04 | 2027-06-25 | 2027-07-09 | 2027-07-23 | 2027-07-30 |  | 2027-07-30 | Not started | Legal (templates and deviations), HRBP (delivery), Payroll (payment)
OF-05 | Final pay, benefits & equity at exit | Process | Offboard | Legally required | HR Operations and Employee Lifecycle | Wave 3 | 2027-05-24 | 2027-06-04 | 2027-06-25 | 2027-07-09 | 2027-07-23 | 2027-07-30 |  | 2027-07-30 | Not started | Payroll (accountable), Benefits and Stock Admin (notices and equity), People Ops (trigger and documents)
OF-06 | Access removal & asset recovery | Process | Offboard | Legally required | HR Operations and Employee Lifecycle | Wave 3 | 2027-05-24 | 2027-06-04 | 2027-06-25 | 2027-07-09 | 2027-07-23 | 2027-07-30 |  | 2027-07-30 | Not started | IT (execution), Security (timing and high-risk cases), People Ops (trigger)
OF-08 | Retirement | Process | Offboard | Legally required | HR Operations and Employee Lifecycle | Wave 3 | 2027-05-24 | 2027-06-04 | 2027-06-25 | 2027-07-09 | 2027-07-23 | 2027-07-30 |  | 2027-07-30 | Not started | HRBP (process), Total Rewards and Stock Admin (retirement benefits and equity), People Ops (execution)
OF-09 | Death of an employee | Process | Offboard | Legally required | HR Operations and Employee Lifecycle | Wave 3 | 2027-05-24 | 2027-06-04 | 2027-06-25 | 2027-07-09 | 2027-07-23 | 2027-07-30 |  | 2027-07-30 | Not started | HRBP (family liaison and process), with Payroll, Benefits and Stock Admin (entitlements) and EHS (work-related deaths)
R-USWA-18 | Silenced No More carve-outs in agreements | Control | Relations | Legally required | Governance, Ethics and Employee Relations | Wave 3 | 2027-05-24 | 2027-06-04 | 2027-06-25 | 2027-07-09 | 2027-07-23 | 2027-07-30 |  | 2027-07-30 | Not started | Employment Legal
R-USWA-19 | Captive-audience meeting control | Control | Relations | Legally required | Governance, Ethics and Employee Relations | Wave 3 | 2027-05-24 | 2027-06-04 | 2027-06-25 | 2027-07-09 | 2027-07-23 | 2027-07-30 |  | 2027-07-30 | Not started | Employee Relations + Employment Legal
R-VN-01 | Vietnam internal labour regulations: consultation, registration & posting | Filing | Relations | Legally required | Governance, Ethics and Employee Relations | Wave 3 | 2027-05-24 | 2027-06-04 | 2027-06-25 | 2027-07-09 | 2027-07-23 | 2027-07-30 |  | 2027-07-30 | Not started | Vietnam HR + Legal
R-VN-04 | Vietnam trade union fee (2% of SI salary fund) | Filing | Relations | Legally required | Governance, Ethics and Employee Relations | Wave 3 | 2027-05-24 | 2027-06-04 | 2027-06-25 | 2027-07-09 | 2027-07-23 | 2027-07-30 |  | 2027-07-30 | Not started | Payroll (Vietnam) + Finance
R-VN-14 | Vietnam DPO, breach notification & data-subject requests | Control | Data | Legally required | HR Data, Safety and Systems | Wave 3 | 2027-05-24 | 2027-06-04 | 2027-06-25 | 2027-07-09 | 2027-07-23 | 2027-07-30 |  | 2027-07-30 | Not started | Privacy + IT Security + Vietnam HR
TA-01 | Job posting & pay-range compliance | Process | Recruit | Legally required | Talent Acquisition | Wave 3 | 2027-05-24 | 2027-06-04 | 2027-06-25 | 2027-07-09 | 2027-07-23 | 2027-07-30 |  | 2027-07-30 | Not started | Talent Acquisition (process), Total Rewards (posted ranges), Legal (jurisdiction rule library)
TA-02 | Sourcing, agencies & referrals | Process | Recruit | Legally required | Talent Acquisition | Wave 3 | 2027-05-24 | 2027-06-04 | 2027-06-25 | 2027-07-09 | 2027-07-23 | 2027-07-30 |  | 2027-07-30 | Not started | Talent Acquisition (process), Ethics & Compliance (sensitive referrals), Legal (agency terms, antitrust), Payroll (referral bonuses)
TA-05 | Background & reference checks | Process | Recruit | Legally required | Talent Acquisition | Wave 3 | 2027-05-24 | 2027-06-04 | 2027-06-25 | 2027-07-09 | 2027-07-23 | 2027-07-30 |  | 2027-07-30 | Not started | Talent Acquisition Operations (process), Legal (screening matrix and adverse decisions), Background-check vendor (execution)
DS-06 | HR vendor & AI tool onboarding | Process | Data | Legally required | HR Data, Safety and Systems | Wave 3 | 2027-05-31 | 2027-06-11 | 2027-07-02 | 2027-07-16 | 2027-07-30 | 2027-08-06 |  | 2027-08-06 | Not started | People Ops (HR tech intake), Legal / Privacy (assessments & AI compliance), Security (vendor risk), Finance / Procurement (contracting)
DS-07 | Employment verification requests | Process | Data | Legally required | HR Data, Safety and Systems | Wave 3 | 2027-05-31 | 2027-06-11 | 2027-07-02 | 2027-07-16 | 2027-07-30 | 2027-08-06 |  | 2027-08-06 | Not started | People Ops (verification desk), Legal (subpoenas & government requests)
EQ-02 | Vesting, release & tax withholding | Process | Equity | Legally required | Total Rewards and Payroll | Wave 3 | 2027-05-31 | 2027-06-11 | 2027-07-02 | 2027-07-16 | 2027-07-30 | 2027-08-06 |  | 2027-08-06 | Not started | Stock Admin (release process), Payroll (income reporting and tax remittance), Tax (withholding rules), Legal (insider rules for sales)
EQ-03 | ESPP enrollment & purchase | Process | Equity | Legally required | Total Rewards and Payroll | Wave 3 | 2027-05-31 | 2027-06-11 | 2027-07-02 | 2027-07-16 | 2027-07-30 | 2027-08-06 |  | 2027-08-06 | Not started | Stock Admin (plan administration), Payroll (contributions and refunds), Total Rewards (plan design), Legal (country feasibility and securities)
EQ-04 | Insider trading pre-clearance & blackouts | Process | Equity | Legally required | Total Rewards and Payroll | Wave 3 | 2027-05-31 | 2027-06-11 | 2027-07-02 | 2027-07-16 | 2027-07-30 | 2027-08-06 |  | 2027-08-06 | Not started | Legal (Securities) - insider trading compliance officer, Stock Admin (broker controls), People Ops (list feeds and acknowledgments)
EQ-05 | Section 16 reporting | Process | Equity | Public-company driven | Total Rewards and Payroll | Wave 3 | 2027-05-31 | 2027-06-11 | 2027-07-02 | 2027-07-16 | 2027-07-30 | 2027-08-06 |  | 2027-08-06 | Not started | Legal (Securities) / Corporate Secretary (filings), Stock Admin (transaction data), People Ops (officer status changes)
EQ-06 | Clawback administration | Process | Equity | Legally required | Total Rewards and Payroll | Wave 3 | 2027-05-31 | 2027-06-11 | 2027-07-02 | 2027-07-16 | 2027-07-30 | 2027-08-06 |  | 2027-08-06 | Not started | Comp Committee (policy administrator), Legal (determination and recovery), Total Rewards (calculation), Finance (restatement and financial measures)
ER-04 | Corrective action & discipline | Process | Relations | Legally required | Governance, Ethics and Employee Relations | Wave 3 | 2027-05-31 | 2027-06-11 | 2027-07-02 | 2027-07-16 | 2027-07-30 | 2027-08-06 |  | 2027-08-06 | Not started | Manager (decision), HRBP (process), Employee Relations (consistency & quality), Legal (dismissal-level review)
ER-05 | Whistleblower & hotline case management | Process | Relations | Public-company driven | Governance, Ethics and Employee Relations | Wave 3 | 2027-05-31 | 2027-06-11 | 2027-07-02 | 2027-07-16 | 2027-07-30 | 2027-08-06 |  | 2027-08-06 | Not started | Ethics & Compliance (program owner), Legal (SOX/SEC matters), Audit Committee (oversight of accounting complaints)
ER-06 | Conflict-of-interest disclosure | Process | Relations | Public-company driven | Governance, Ethics and Employee Relations | Wave 3 | 2027-05-31 | 2027-06-11 | 2027-07-02 | 2027-07-16 | 2027-07-30 | 2027-08-06 |  | 2027-08-06 | Not started | Ethics & Compliance (program), Legal (executive & related-person items), Manager (mitigation)
ER-07 | Threat assessment & workplace violence | Process | Relations | Legally required | Governance, Ethics and Employee Relations | Wave 3 | 2027-05-31 | 2027-06-11 | 2027-07-02 | 2027-07-16 | 2027-07-30 | 2027-08-06 |  | 2027-08-06 | Not started | Security (Threat Assessment Team lead), Employee Relations (people actions), EHS (WVPP / OHSA program compliance), Legal
ER-08 | Labor relations & employee consultation | Process | Relations | Legally required | Governance, Ethics and Employee Relations | Wave 3 | 2027-05-31 | 2027-06-11 | 2027-07-02 | 2027-07-16 | 2027-07-30 | 2027-08-06 |  | 2027-08-06 | Not started | Employee Relations (global labor relations), country HR leads (local bodies), Legal (labor counsel)
ER-09 | Legal hold & litigation support | Process | Relations | Legally required | Governance, Ethics and Employee Relations | Wave 3 | 2027-05-31 | 2027-06-11 | 2027-07-02 | 2027-07-16 | 2027-07-30 | 2027-08-06 |  | 2027-08-06 | Not started | Legal (hold owner), People Ops (HR record custodian), IT (system preservation)
HS-01 | Incident & injury reporting | Process | Safety | Legally required | HR Data, Safety and Systems | Wave 3 | 2027-05-31 | 2027-06-11 | 2027-07-02 | 2027-07-16 | 2027-07-30 | 2027-08-06 |  | 2027-08-06 | Not started | EHS (process), line managers (scene control and corrective actions), Legal (serious incidents and regulator contact)
HS-02 | Crisis response & duty of care | Process | Safety | Legally required | HR Data, Safety and Systems | Wave 3 | 2027-05-31 | 2027-06-11 | 2027-07-02 | 2027-07-16 | 2027-07-30 | 2027-08-06 |  | 2027-08-06 | Not started | Security (crisis management and travel risk), HRBP (people support), People Ops (rosters), EHS (site emergency plans)
HS-03 | Lab & EHS safety program | Process | Safety | Legally required | HR Data, Safety and Systems | Wave 3 | 2027-05-31 | 2027-06-11 | 2027-07-02 | 2027-07-16 | 2027-07-30 | 2027-08-06 |  | 2027-08-06 | Not started | EHS (program), lab managers (daily compliance), Security (lab access), Facilities (engineering controls)
LV-04 | Occupational injury & workers' comp claims | Process | Leave | Legally required | Talent, Leave and Engagement | Wave 3 | 2027-05-31 | 2027-06-11 | 2027-07-02 | 2027-07-16 | 2027-07-30 | 2027-08-06 |  | 2027-08-06 | Not started | Benefits (claims process), EHS (recording and investigation through HS-01), Payroll (wage continuation), carrier or statutory board (adjudication)
LV-05 | PTO & holiday administration | Process | Leave | Legally required | Talent, Leave and Engagement | Wave 3 | 2027-05-31 | 2027-06-11 | 2027-07-02 | 2027-07-16 | 2027-07-30 | 2027-08-06 |  | 2027-08-06 | Not started | People Ops (process and configuration), Total Rewards (policy), Payroll (vacation pay and payouts), Managers (approvals)
OF-10 | Alumni, references & rehire eligibility | Process | Offboard | Legally required | HR Operations and Employee Lifecycle | Wave 3 | 2027-05-31 | 2027-06-11 | 2027-07-02 | 2027-07-16 | 2027-07-30 | 2027-08-06 |  | 2027-08-06 | Not started | People Ops (references, verification, certificates), HRBP (rehire eligibility), Recruiter (alumni and boomerang pipeline)
ON-02 | Right-to-work verification | Process | Onboard | Legally required | HR Operations and Employee Lifecycle | Wave 3 | 2027-05-31 | 2027-06-11 | 2027-07-02 | 2027-07-16 | 2027-07-30 | 2027-08-06 |  | 2027-08-06 | Not started | People Ops (process), Immigration (foreign-national permits), Legal (I-9 and E-Verify policy)
ON-03 | Hire transaction & HRIS setup | Process | Onboard | Legally required | HR Operations and Employee Lifecycle | Wave 3 | 2027-05-31 | 2027-06-11 | 2027-07-02 | 2027-07-16 | 2027-07-30 | 2027-08-06 |  | 2027-08-06 | Not started | People Ops (process and data), Payroll (payroll acceptance), Finance (cost center and SOX control owner)
ON-05 | Relocation | Process | Onboard | Legally required | HR Operations and Employee Lifecycle | Wave 3 | 2027-05-31 | 2027-06-11 | 2027-07-02 | 2027-07-16 | 2027-07-30 | 2027-08-06 |  | 2027-08-06 | Not started | Mobility (process and vendor), Total Rewards (package design), Payroll (tax reporting), Legal (repayment agreements)
PD-01 | Goal setting & check-ins | Process | Grow | Legally required | Talent, Leave and Engagement | Wave 3 | 2027-05-31 | 2027-06-11 | 2027-07-02 | 2027-07-16 | 2027-07-30 | 2027-08-06 |  | 2027-08-06 | Not started | HRBP (process), Managers (execution), People Ops (system configuration)
PD-04 | Promotion | Process | Grow | Legally required | Talent, Leave and Engagement | Wave 3 | 2027-05-31 | 2027-06-11 | 2027-07-02 | 2027-07-16 | 2027-07-30 | 2027-08-06 |  | 2027-08-06 | Not started | HRBP (process), Dept Head (approval), Total Rewards (pricing)
PY-02 | Off-cycle & manual payments | Process | Pay | Legally required | Total Rewards and Payroll | Wave 3 | 2027-05-31 | 2027-06-11 | 2027-07-02 | 2027-07-16 | 2027-07-30 | 2027-08-06 |  | 2027-08-06 | Not started | Payroll (process), Finance (approval and SOX control owner), HRBP/People Ops (requesters)
PY-03 | Time, attendance & overtime | Process | Pay | Legally required | Total Rewards and Payroll | Wave 3 | 2027-05-31 | 2027-06-11 | 2027-07-02 | 2027-07-16 | 2027-07-30 | 2027-08-06 |  | 2027-08-06 | Not started | Payroll (process and calculation), Manager (approval), HRBP (policy, caps and remediation), People Ops (classification data)
PY-04 | Year-end & statutory payroll filings | Process | Pay | Legally required | Total Rewards and Payroll | Wave 3 | 2027-05-31 | 2027-06-11 | 2027-07-02 | 2027-07-16 | 2027-07-30 | 2027-08-06 |  | 2027-08-06 | Not started | Payroll (process), Finance/Tax (review and sign-off), Benefits (ACA data), Stock Admin (equity income true-up)
PY-05 | Payroll error correction & overpayment recovery | Process | Pay | Legally required | Total Rewards and Payroll | Wave 3 | 2027-05-31 | 2027-06-11 | 2027-07-02 | 2027-07-16 | 2027-07-30 | 2027-08-06 |  | 2027-08-06 | Not started | Payroll (process), HRBP (employee communication), Legal (recovery method outside standard templates), Finance (write-off approval)
R-017 | India statutory appointment letter | Record | Onboard | Legally required | HR Operations and Employee Lifecycle | Wave 3 | 2027-05-31 | 2027-06-11 | 2027-07-02 | 2027-07-16 | 2027-07-30 | 2027-08-06 |  | 2027-08-06 | Not started | India HR Ops
R-110 | China PIPL HR compliance file (PIPIA, cross-border transfer pathway, audits) | Record | Data | Legally required | HR Data, Safety and Systems | Wave 3 | 2027-05-31 | 2027-06-11 | 2027-07-02 | 2027-07-16 | 2027-07-30 | 2027-08-06 |  | 2027-08-06 | Not started | Privacy + China HR + Legal
R-143 | Taiwan separation certificates & insurance withdrawal | Record | Offboard | Legally required | HR Operations and Employee Lifecycle | Wave 3 | 2027-05-31 | 2027-06-11 | 2027-07-02 | 2027-07-16 | 2027-07-30 | 2027-08-06 |  | 2027-08-06 | Not started | Taiwan HR + Payroll
TA-07 | Immigration sponsorship for new hires | Process | Recruit | Legally required | Talent Acquisition | Wave 3 | 2027-05-31 | 2027-06-11 | 2027-07-02 | 2027-07-16 | 2027-07-30 | 2027-08-06 |  | 2027-08-06 | Not started | Immigration (process), Talent Acquisition (candidate), Dept Head (cost approval), Legal (policy)
TA-08 | University & intern hiring | Process | Recruit | Legally required | Talent Acquisition | Wave 3 | 2027-05-31 | 2027-06-11 | 2027-07-02 | 2027-07-16 | 2027-07-30 | 2027-08-06 |  | 2027-08-06 | Not started | University Recruiting (Talent Acquisition), Hiring Managers (projects), L&D (program), Legal (student-status and pay rules)
TA-09 | Executive hiring | Process | Recruit | Public-company driven | Talent Acquisition | Wave 3 | 2027-05-31 | 2027-06-11 | 2027-07-02 | 2027-07-16 | 2027-07-30 | 2027-08-06 |  | 2027-08-06 | Not started | CHRO (process), Comp Committee (pay approval), Legal and Corporate Secretary (disclosure and Section 16)
ER-10 | Trade-secret protection for departing employees | Process | Relations | Legally required | Governance, Ethics and Employee Relations | Wave 3 | 2027-06-07 | 2027-06-18 | 2027-07-09 | 2027-07-23 | 2027-08-06 | 2027-08-13 |  | 2027-08-13 | Not started | Security / Insider Risk (lead), Legal (IP & employment), HRBP (process), IT (access & devices)
PD-05 | Talent review & succession | Process | Grow | Legally required | Talent, Leave and Engagement | Wave 3 | 2027-06-07 | 2027-06-18 | 2027-07-09 | 2027-07-23 | 2027-08-06 | 2027-08-13 |  | 2027-08-13 | Not started | CHRO (enterprise plan), HRBPs (org reviews), Board Nominating/Governance Committee (CEO succession)
PD-07 | Learning programs & tuition assistance | Process | Grow | Legally required | Talent, Leave and Engagement | Wave 3 | 2027-06-07 | 2027-06-18 | 2027-07-09 | 2027-07-23 | 2027-08-06 | 2027-08-13 |  | 2027-08-13 | Not started | L&D (program), Legal (agreement templates), Payroll (tax treatment)
R-028 | Taiwan employee roster, wage & minute-level attendance records; overtime consents | Record | Pay | Legally required | Total Rewards and Payroll | Wave 3 | 2027-06-07 | 2027-06-18 | 2027-07-09 | 2027-07-23 | 2027-08-06 | 2027-08-13 |  | 2027-08-13 | Not started | Taiwan HR + Payroll
R-033 | California pay-scale requests & job title/wage history records | Record | Reward | Legally required | Total Rewards and Payroll | Wave 3 | 2027-06-07 | 2027-06-18 | 2027-07-09 | 2027-07-23 | 2027-08-06 | 2027-08-13 |  | 2027-08-13 | Not started | Total Rewards + People Ops
R-055 | ERISA & HIPAA plan documentation (SPD/SMM, NQTL analysis, HIPAA firewall) | Record | Benefits | Legally required | Total Rewards and Payroll | Wave 3 | 2027-06-07 | 2027-06-18 | 2027-07-09 | 2027-07-23 | 2027-08-06 | 2027-08-13 |  | 2027-08-13 | Not started | Benefits + Employment Legal (ERISA) + Privacy
R-145 | China termination certificate & 15-day file/social-insurance transfer | Record | Offboard | Legally required | HR Operations and Employee Lifecycle | Wave 3 | 2027-06-07 | 2027-06-18 | 2027-07-09 | 2027-07-23 | 2027-08-06 | 2027-08-13 |  | 2027-08-13 | Not started | China HR + Payroll/HR agency
R-DE-01 | Germany written statement of essential terms (Nachweis) | Record | Onboard | Legally required | HR Operations and Employee Lifecycle | Wave 3 | 2027-06-07 | 2027-06-18 | 2027-07-09 | 2027-07-23 | 2027-08-06 | 2027-08-13 |  | 2027-08-13 | Not started | Germany HR Ops + Legal
R-IL-19 | Pre-dismissal hearing (shimua) record | Record | Offboard | Legally required | HR Operations and Employee Lifecycle | Wave 3 | 2027-06-07 | 2027-06-18 | 2027-07-09 | 2027-07-23 | 2027-08-06 | 2027-08-13 |  | 2027-08-13 | Not started | HRBP + Employment Legal
R-USCO-02 | Job description and wage-rate history records | Record | Reward | Legally required | Total Rewards and Payroll | Wave 3 | 2027-06-07 | 2027-06-18 | 2027-07-09 | 2027-07-23 | 2027-08-06 | 2027-08-13 |  | 2027-08-13 | Not started | People Ops + Total Rewards
R-USCO-10 | POWR Act harassment program and complaint repository | Record | Relations | Legally required | Governance, Ethics and Employee Relations | Wave 3 | 2027-06-07 | 2027-06-18 | 2027-07-09 | 2027-07-23 | 2027-08-06 | 2027-08-13 |  | 2027-08-13 | Not started | Employee Relations + Employment Legal
R-USNC-10 | OSHANC injury reporting and recordkeeping | Record | Safety | Legally required | HR Data, Safety and Systems | Wave 3 | 2027-06-07 | 2027-06-18 | 2027-07-09 | 2027-07-23 | 2027-08-06 | 2027-08-13 |  | 2027-08-13 | Not started | EHS
R-USTX-03 | Written wage-deduction authorizations file | Record | Pay | Legally required | Total Rewards and Payroll | Wave 3 | 2027-06-07 | 2027-06-18 | 2027-07-09 | 2027-07-23 | 2027-08-06 | 2027-08-13 |  | 2027-08-13 | Not started | Payroll + HR Operations
R-USTX-13 | AI system inventory and documentation (TRAIGA) | Record | Data | Legally required | HR Data, Safety and Systems | Wave 3 | 2027-06-07 | 2027-06-18 | 2027-07-09 | 2027-07-23 | 2027-08-06 | 2027-08-13 |  | 2027-08-13 | Not started | HR Analytics + Privacy + Employment Legal
R-USWA-13 | Personnel file and discharge-statement requests | Record | Data | Legally required | HR Data, Safety and Systems | Wave 3 | 2027-06-07 | 2027-06-18 | 2027-07-09 | 2027-07-23 | 2027-08-06 | 2027-08-13 |  | 2027-08-13 | Not started | HR Ops + Employment Legal
R-VN-06 | Vietnam labour management book, labour registration & usage reports | Record | Governance | Legally required | Governance, Ethics and Employee Relations | Wave 3 | 2027-06-07 | 2027-06-18 | 2027-07-09 | 2027-07-23 | 2027-08-06 | 2027-08-13 |  | 2027-08-13 | Not started | Vietnam HR Ops
R-VN-17 | Vietnam disciplinary meeting notices, minutes & decisions | Record | Relations | Legally required | Governance, Ethics and Employee Relations | Wave 3 | 2027-06-07 | 2027-06-18 | 2027-07-09 | 2027-07-23 | 2027-08-06 | 2027-08-13 |  | 2027-08-13 | Not started | Employee Relations + Vietnam HR
TA-10 | Rehire, relatives & conflict screening | Process | Recruit | Legally required | Talent Acquisition | Wave 3 | 2027-06-07 | 2027-06-18 | 2027-07-09 | 2027-07-23 | 2027-08-06 | 2027-08-13 |  | 2027-08-13 | Not started | Talent Acquisition (questionnaire), Ethics & Compliance (FCPA and conflicts), Legal (restrictive covenants and Item 404)
TA-11 | Candidate privacy & data retention | Process | Recruit | Legally required | Talent Acquisition | Wave 3 | 2027-06-07 | 2027-06-18 | 2027-07-09 | 2027-07-23 | 2027-08-06 | 2027-08-13 |  | 2027-08-13 | Not started | Legal (Privacy) as policy owner; TA Operations as process and ATS configuration owner
POL-07 | Workplace Relationships & Employment of Relatives | Policy | Governance | Best practice | Governance, Ethics and Employee Relations | Wave 4 | 2027-08-16 | 2027-08-20 | 2027-09-03 | 2027-09-10 | 2027-09-17 | 2027-09-24 |  | 2027-09-24 | Not started | HR (Employee Relations)
POL-22 | Early Careers & Internships | Policy | Recruit | Best practice | Talent Acquisition | Wave 4 | 2027-08-16 | 2027-08-20 | 2027-09-03 | 2027-09-10 | 2027-09-17 | 2027-09-24 |  | 2027-09-24 | Not started | Talent Acquisition (University Programs)
POL-23 | Compensation Philosophy & Pay Administration | Policy | Reward | Best practice | Total Rewards and Payroll | Wave 4 | 2027-08-16 | 2027-08-20 | 2027-09-03 | 2027-09-10 | 2027-09-17 | 2027-09-24 |  | 2027-09-24 | Not started | Total Rewards
POL-38 | Hybrid & Remote Work | Policy | Move | Best practice | HR Operations and Employee Lifecycle | Wave 4 | 2027-08-16 | 2027-08-20 | 2027-09-03 | 2027-09-10 | 2027-09-17 | 2027-09-24 |  | 2027-09-24 | Not started | HR Policy (People Ops) with Workplace/Facilities
POL-40 | Global Mobility | Policy | Move | Best practice | HR Operations and Employee Lifecycle | Wave 4 | 2027-08-16 | 2027-08-20 | 2027-09-03 | 2027-09-10 | 2027-09-17 | 2027-09-24 |  | 2027-09-24 | Not started | Global Mobility (with Immigration and Tax)
POL-42 | Performance Management | Policy | Grow | Best practice | Talent, Leave and Engagement | Wave 4 | 2027-08-16 | 2027-08-20 | 2027-09-03 | 2027-09-10 | 2027-09-17 | 2027-09-24 |  | 2027-09-24 | Not started | Talent Management with HR Business Partners
R-113 | HR data breach & cyber incident response playbook | Program | Data | Best practice | HR Data, Safety and Systems | Wave 4 | 2027-08-16 | 2027-08-20 | 2027-09-03 | 2027-09-10 | 2027-09-17 | 2027-09-24 |  | 2027-09-24 | Not started | Privacy + IT Security + Legal + HR Ops
POL-25 | Variable Pay & Bonus | Policy | Reward | Best practice | Total Rewards and Payroll | Wave 4 | 2027-08-23 | 2027-08-27 | 2027-09-10 | 2027-09-17 | 2027-09-24 | 2027-10-01 |  | 2027-10-01 | Not started | Total Rewards with Finance (FP&A)
POL-32 | Employee Referral Program | Policy | Reward | Best practice | Total Rewards and Payroll | Wave 4 | 2027-08-23 | 2027-08-27 | 2027-09-10 | 2027-09-17 | 2027-09-24 | 2027-10-01 |  | 2027-10-01 | Not started | Talent Acquisition
POL-43 | Promotion & Internal Mobility | Policy | Grow | Best practice | Talent, Leave and Engagement | Wave 4 | 2027-08-23 | 2027-08-27 | 2027-09-10 | 2027-09-17 | 2027-09-24 | 2027-10-01 |  | 2027-10-01 | Not started | Talent Management with Talent Acquisition
POL-52 | Resignation, Notice & Garden Leave | Policy | Offboard | Best practice | HR Operations and Employee Lifecycle | Wave 4 | 2027-08-23 | 2027-08-27 | 2027-09-10 | 2027-09-17 | 2027-09-24 | 2027-10-01 |  | 2027-10-01 | Not started | People Ops (Offboarding) with Employee Relations
R-USCO-19 | Colorado harassment and fair-hiring training | Training | Relations | Best practice | Governance, Ethics and Employee Relations | Wave 4 | 2027-08-23 | 2027-08-27 | 2027-09-10 | 2027-09-17 | 2027-09-24 | 2027-10-01 |  | 2027-10-01 | Not started | L&D + Employee Relations + TA Ops
POL-44 | Learning & Tuition Assistance | Policy | Grow | Best practice | Talent, Leave and Engagement | Wave 4 | 2027-08-30 | 2027-09-03 | 2027-09-17 | 2027-09-24 | 2027-10-01 | 2027-10-08 |  | 2027-10-08 | Not started | Learning & Development
POL-56 | References & Employment Verification | Policy | Offboard | Best practice | HR Operations and Employee Lifecycle | Wave 4 | 2027-08-30 | 2027-09-03 | 2027-09-17 | 2027-09-24 | 2027-10-01 | 2027-10-08 |  | 2027-10-08 | Not started | People Ops (Employment Verification)
R-081 | Protected-activity check before adverse action | Control | Relations | Best practice | Governance, Ethics and Employee Relations | Wave 4 | 2027-08-30 | 2027-09-03 | 2027-09-17 | 2027-09-24 | 2027-10-01 | 2027-10-08 |  | 2027-10-08 | Not started | Employee Relations + Employment Legal + HRBP
R-USTX-07 | Non-subscriber occupational injury benefit plan (if opting out) | Program | Benefits | Best practice | Total Rewards and Payroll | Wave 4 | 2027-08-30 | 2027-09-03 | 2027-09-17 | 2027-09-24 | 2027-10-01 | 2027-10-08 |  | 2027-10-08 | Not started | Benefits + Risk Management + Legal
R-USTX-18 | Texas restrictive covenant program | Program | Offboard | Best practice | HR Operations and Employee Lifecycle | Wave 4 | 2027-08-30 | 2027-09-03 | 2027-09-17 | 2027-09-24 | 2027-10-01 | 2027-10-08 |  | 2027-10-08 | Not started | Employment Legal + Total Rewards + HRBPs
Formulas:
Go live (current) = IF([Go live (override)]<>"",[Go live (override)],[Go live (plan)])
Overdue = IF(AND([Go live (current)]<TODAY(),[Status]<>"Approved",[Status]<>"Live",[Status]<>"Not applicable"),"Overdue","")
Days late = IF([Overdue]="Overdue",TODAY()-[Go live (current)],"")

## Milestones
ID | Date | Milestone | Wave | Type | Done when
M01 | 2026-10-12 | Project kickoff | W0 | event | Kickoff held with sponsor, workstream leads, regional HR leads and Legal.
M02 | 2026-10-23 | Charter approved | W0 | gate | Steering committee approves charter, scope, resourcing and governance.
M03 | 2026-10-30 | Approval chains configured | W0 | deliverable | Every chain has named approvers; test submission run end to end.
M04 | 2026-11-06 | Baseline complete and Mobilize gate | W0 | gate | All 438 items have an owner, a current-state rating and a wave; plan v1.0 baselined.
M05 | 2026-11-09 | Wave 1 starts | W1 | event | Wave 1 items in Discover; workshops scheduled.
M06 | 2026-12-18 | Wave 1 drafts complete | W1 | deliverable | All Wave 1 drafts submitted for review before the year-end freeze.
M07 | 2027-01-29 | Wave 1 approvals complete | W1 | gate | Every Wave 1 approval chain closed; works council consultations started where required.
M08 | 2027-02-12 | Wave 1 live | W1 | gate | Wave 1 published, communicated and evidenced; wave retrospective held.
M09 | 2027-02-15 | Wave 2 starts | W2 | event | Wave 2 items in Discover.
M10 | 2027-04-09 | Wave 2 drafts complete | W2 | deliverable | All Wave 2 drafts submitted for review.
M11 | 2027-05-14 | Wave 2 live | W2 | gate | Wave 2 published, communicated and evidenced.
M12 | 2027-05-17 | Wave 3 starts | W3 | event | Wave 3 items in Discover.
M13 | 2027-07-09 | Wave 3 drafts complete | W3 | deliverable | All Wave 3 drafts submitted for review.
M14 | 2027-08-13 | Wave 3 live: all required items done | W3 | gate | Every legal, public-company and semiconductor item is live with evidence.
M15 | 2027-09-10 | Global attestation campaign launched | W4 | event | All employees asked to acknowledge the updated Code and core policies.
M16 | 2027-09-24 | Audit readiness review | W4 | gate | Internal Audit samples 40 items and confirms evidence is complete.
M17 | 2027-10-01 | Handover to business as usual | W4 | deliverable | Every item has a named owner, a review date and a place in the annual review calendar.
M18 | 2027-10-08 | Project close | W4 | gate | Close-out report and lessons learned approved by the steering committee.

## Risks
ID | Risk | Detail | Likelihood | Impact | Score | Owner | Mitigation | Trigger | Status
R01 | Germany works council co-determination delays | Where a works council exists at a German establishment, policies on conduct rules (BetrVG §87(1) no.1), working time (nos.2-3), technical tools able to monitor behaviour or performance such as the HRIS, M365 and DLP (no.6), pay and bonus principles (nos.10-11), mobile work (no.14) and health protection must be adopted as works agreements. The council can enjoin a unilateral rollout, and an unresolved dispute goes to the Einigungsstelle, which can push German effective dates months past the global date. | Medium | High | 6 | Regional HR lead (EMEA) | Confirm by 30 Oct 2026 whether a works council exists at each German establishment. Tag every co-determined item in Atlas at Discover. Brief the council on the Atlas scope in November, group co-determined topics into one framework works agreement with annexes, and open consultation on Wave 1 items by 29 Jan 2027 (M07). Publish global policies with a German addendum that names the sections applying only once the works agreement is signed. | No agreement in principle 6 weeks after consultation opens, or the council asks for the Einigungsstelle. | Open
R02 | China democratic procedure not completed or not evidenced | Rules on pay, hours, leave, safety, discipline and training must be discussed with the employee congress or all employees, finalised after consultation with the union or employee representatives and publicised with signed acknowledgment (Labor Contract Law Art. 4). If a step is skipped or the records are missing, the handbook cannot support an Art. 39 dismissal. The Lunar New Year freeze (5 to 14 Feb 2027) removes the last two weeks of Wave 1. | Medium | High | 6 | Country HR lead, China | Run one consolidated democratic procedure per wave covering Shanghai and Shenzhen, not one per policy. Use a bilingual handbook with Chinese prevailing. Hold the Wave 1 procedure from 6 to 29 Jan 2027 and publish after the freeze. File meeting notices, sign-in sheets, the comment log, consultation minutes and signed acknowledgments in Atlas before the item can move to Go live. | A China item reaches Approve without consultation records, or acknowledgment is below 95% two weeks after publication. | Open
R03 | Vietnam internal labour regulations registration delays | Rules on working time, discipline, sexual harassment, protection of secrets and material liability bind employees only once they sit in internal labour regulations (ILR) that were consulted with the grassroots union, registered with the provincial Department of Home Affairs within 10 days of issue and posted at the workplace. ILR take effect 15 days after the authority receives a complete dossier, and discipline is valid only on registered grounds. An incomplete dossier restarts the clock. | Medium | High | 6 | Country HR lead, Vietnam | Batch ILR changes into one registration per wave. Have local counsel pre-check the Vietnamese dossier before submission. Keep the current registered ILR in force until the new version takes effect, and schedule union consultation and submission outside the Tet freeze (5 to 14 Feb 2027). | Dossier returned as incomplete, or no proof of receipt within 10 working days of submission. | Open
R04 | Taiwan work rules filing and approval | With 30 or more employees, work rules must be submitted to the local labor authority (the Science Park Bureau for Hsinchu Science Park sites) for approval, posted, and refiled on every amendment. Global policies are not enforceable locally unless they are incorporated. Overtime and flexible-hours changes also need consent at the quarterly labor-management meeting, so authority comments or a missed meeting can hold Taiwan launches past the wave date. | Medium | Medium | 4 | Country HR lead, Taiwan | Map each global policy to a work-rule chapter at Discover. File one consolidated Traditional Chinese amendment per wave, timed to the quarterly labor-management meeting. Ask local counsel to pre-review each filing, and keep the approved work rules as the local source of truth until the amendment is approved. | The authority asks for revisions, or approval has not arrived 8 weeks after filing. | Open
R05 | Translation quality and lead time | Local versions are needed in at least German, Hebrew, Simplified Chinese, Traditional Chinese, Vietnamese, Kannada, Telugu and Spanish. In China, Taiwan and Vietnam the local text is what authorities and courts rely on. Translating drafts that later change, or using translators without HR and legal terminology, creates rework and legal exposure. | High | Medium | 6 | HR Change and Communications lead | Translate only after Legal review (policy chain step s3) is complete. Use one vendor with an HR and legal glossary and translation memory, and require in-country review by the Country HR lead within 5 business days. Plan 10 business days per batch and send batches weekly. | More than 10% of translated documents come back with substantive errors, or a batch takes more than 10 business days. | Open
R06 | Legal review bottleneck | Employment counsel reviews every policy (policy chain step s3) and every legal obligation (obligation chain step s2). Wave 1 drafts all arrive before 18 Dec 2026, so the review queue peaks around the year-end freeze, when local counsel are also slow to respond. | High | High | 9 | Employment counsel | Tier reviews by risk so process documents without legal content get a light review. Build a clause library for repeated text (non-retaliation, NLRA savings clause, whistleblower carve-outs, privacy notices). Engage a local counsel panel on fixed-fee bundles per country. Set a 5-business-day review target and publish queue age in the weekly PMO status report. | More than 40 items waiting for Legal review, or a median wait above 7 business days for two weeks in a row. | Open
R07 | SME availability during year-end, SOX testing and the annual cycle | Payroll, Stock Administration, Total Rewards and HRIS experts carry year-end payroll, W-2 and tax-year changes, Q4 SOX testing, the 10-K and the annual compensation cycle between December and March. Wave 1 drafting and approval fall in the same window. | High | Medium | 6 | Head of Total Rewards | Run WS4 and WS6 Discover workshops in November. Keep payroll and stock administration experts off Atlas drafting from 14 Dec 2026 to 29 Jan 2027 except for approvals. Agree backfill or contract writers for documentation, and move lower-risk WS4 items to Wave 2. | More than 20% of scheduled SME workshops in a month are cancelled or moved. | Open
R08 | Holiday freezes compress Wave 1 | The year-end freeze (21 Dec 2026 to 1 Jan 2027) allows no approvals or launches, and the Lunar New Year and Tet freeze (5 to 14 Feb 2027) covers the last two weeks before Wave 1 goes live on 12 Feb 2027. Any slip in December drafts pushes approvals into late January with no slack. | High | Medium | 6 | HR Program Manager | Hold the 18 Dec 2026 draft deadline (M06) and run a readiness check on 11 Dec. Book approver time in the first two weeks of January. Set China, Taiwan and Vietnam local effective dates after the Lunar New Year freeze from the start, so the 12 Feb milestone covers only global publication for those countries. | More than 15% of Wave 1 drafts not submitted by 18 Dec 2026. | Open
R09 | Approver turnover or unavailability | Each chain step is held by a role. If an approver leaves, changes role or goes on leave, items stall, especially at steps with the 'all' rule such as Regional HR review in the policy chain, where all three regions must sign. | Medium | Medium | 4 | HR Program Manager | Name a primary and a delegate for every chain step. Reconcile the approver roster with HRIS org data monthly. Escalate any step idle for 5 business days to the workstream lead, then to the steering committee. | An approval step is idle for more than 5 business days, or an approver's HRIS record shows a role change, leave or termination. | Open
R10 | Scope creep from new laws | Laws taking effect during the program will change items already in flight, for example California CCPA automated decision-making duties (1 Jan 2027), Colorado SB 26-189 AI notices (1 Jan 2027, replacing SB 24-205), India DPDP notice and consent duties (13 May 2027), the Washington noncompete ban (30 June 2027), California SB 947 (1 Jul 2027 if signed), Texas laws from the 2027 session (usually effective 1 Sep 2027) and German transposition of the EU Pay Transparency Directive, which missed the 7 June 2026 deadline with a bill expected in early 2027. | High | Medium | 6 | Employment counsel | Run a monthly legal change scan against the library watchlists. Add or reopen items only through a change request decided by the steering committee. Hold about 10% of Wave 3 and Wave 4 capacity for law changes, and give every item a review date so later changes go to business-as-usual owners. | A new law or rule with an effective date before 8 Oct 2027 affects a live or in-flight item. | Open
R11 | Inconsistent current-state documents | Existing policies sit in several places (intranet pages, the HRIS document library, country shared drives, offer and handbook templates), often in conflicting versions. Owners may draft from an out-of-date source, and old copies left online contradict the approved version. | High | Medium | 6 | Workstream leads | At Discover, collect every version and record the source of truth in Atlas. Rate each item's current state on the standard scale. At Go live, retire or redirect superseded copies and file the retirement as evidence. | More than 25% of Wave 1 items are rated as having conflicting current documents at Discover. | Open
R12 | HRIS (Darwinbox) configuration dependencies | Changes to leave, attendance, time recording, probation, letters and acknowledgments need Darwinbox configuration before a policy or process can go live. HRIS release windows and testing are not in the Atlas stage durations, and in Germany a change to a system able to monitor behaviour or performance may itself need a works agreement. | Medium | High | 6 | Director, HRIS and People Analytics | Flag 'system change needed' at Discover and open the HRIS ticket during Draft. Keep a joint backlog and align effective dates to the HRIS release calendar. Use the process chain publish step (s4) to confirm systems are ready before approval. | An item reaches Approve with an HRIS ticket not scheduled before its planned effective date. | Open
R13 | Change fatigue | Four waves of policy changes, acknowledgments and manager briefings over 12 months, on top of the performance and compensation cycles, risk employees and managers ignoring Atlas communications. | Medium | Medium | 4 | HR Change and Communications lead | Bundle each wave into one launch message and one acknowledgment request. Limit all-employee asks to two per wave. Give managers a one-page summary of what changed and why for each wave, and use local languages for country launches. | Manager briefing attendance below 60%, or wave acknowledgment below 85% two weeks after launch. | Open
R14 | Attestation non-completion | The global attestation campaign (M15, 10 Sep 2027) asks every employee to acknowledge the updated Code and core policies before the audit readiness review on 24 Sep 2027. Employees on leave, lab and operations staff with little desk time, and recent joiners pull completion down. | Medium | High | 6 | Head of Employee Relations | Run the campaign in local languages, give managers daily completion dashboards, send reminders on days 5 and 10 and escalate to HRBPs on day 12. Track employees on leave separately and attest them on return. In China and Vietnam, collect acknowledgments in the signed form the local process requires. | Completion below 80% on day 10 of the campaign. | Open
R15 | Evidence gaps found at audit | Internal Audit will sample 40 items at the audit readiness review (M16, 24 Sep 2027). Missing approval records, unfiled consultation minutes or unposted notices would undercut the claim that items are live and could become findings on SOX-relevant HR controls. | Medium | High | 6 | HR Program Manager | Make evidence an exit criterion for every stage. From March 2027, spot-check 10% of live items each month using the Internal Audit sampling method, and run a mock sample of 20 items in August 2027. | A monthly spot-check finds more than 5% of sampled live items with incomplete evidence. | Open
R16 | Deemed export process ownership disputes | Deemed export screening, license determinations, the export-control role flag and access deprovisioning involve Trade Compliance, Talent Acquisition, Immigration, HR Operations and IT Security. Without one accountable owner per control, these semiconductor items cannot leave Discover, and start dates or system access may be released without clearance. | Medium | High | 6 | Director, Talent Acquisition Operations | Agree a RACI for the deemed export items at the steering committee before 6 Nov 2026: Trade Compliance accountable for license determinations, Talent Acquisition for the role flag and start-date gate, HR Operations and IT Security for deprovisioning. Route the items through the public company and semiconductor chain with Trade Compliance at step s2. | Any deemed export item still has no agreed accountable owner at the Mobilize gate (M04, 6 Nov 2026). | Open
R17 | Privacy of HR data held in Atlas | Evidence uploads (investigation files, signed acknowledgments, consultation minutes, sample letters) can bring employee personal data into Atlas, which is used from several countries. That raises cross-border transfer and retention questions under GDPR, China PIPL, Vietnam PDPL, Israel's Amendment 13 and India's DPDP rules. | Medium | High | 6 | Director, HRIS and People Analytics | Keep Atlas to policies, process documents and evidence of completion, and link to the system of record for personal data instead of uploading it. Redact samples. Set role-based access and a retention rule, and complete a privacy review with the Privacy Office before Wave 1 starts. | A monthly scan finds personal data in an Atlas upload, or a country privacy lead raises a transfer concern. | Open
R18 | India labour codes transition | The four Labour Codes took effect on 21 Nov 2025 and central rules were finalised on 8 May 2026, but Karnataka and Telangana rules are largely still in draft, and the status of the Karnataka IT/ITeS standing-orders exemption under the IR Code is unconfirmed. India addenda drafted now may need rework when state rules are final. | High | Medium | 6 | Regional HR lead (APAC) | Draft India addenda against the central rules and the draft state rules, with a 'state rules pending' flag in Atlas. Have local counsel confirm worker versus employee classification for engineering roles. Recheck flagged items within 30 days of final state rules. | Karnataka or Telangana publishes final rules under the Codes, or a notification on the IT/ITeS exemption is issued. | Open
R19 | Approval cycle time slower than plan | The global policy chain has six steps, including Regional HR review where all three regions must sign, and the plan allows two weeks for Approve. Sequential sign-offs and returned drafts can double that. | Medium | Medium | 4 | HR Program Manager | Have regional HR comment during Review so step s4 is a confirmation. Set a 3-business-day target per step, send automatic reminders and review an ageing report at the weekly workstream lead meeting. | Median time in Approve above 15 business days in any wave. | Open
R20 | Workstream lead and owner capacity | Workstream leads and item owners keep their day jobs. The performance and compensation cycle, open requisitions and employee relations cases compete with Atlas work throughout the year. | Medium | High | 6 | Chief People Officer | Agree protected time for leads and owners in the charter. Track planned against actual hours monthly. Move lower-risk items to later waves before deadlines slip, and fund contract writers for process documentation. | A workstream is more than 10% behind plan on items for three consecutive weeks. | Open
R21 | Israel collective agreement and Hebrew requirements | Where a collective agreement applies, policy changes affecting employment conditions must be negotiated, and Histadrut organizing in tech has grown. Statutory notices, the sexual harassment prevention bylaw and workplace postings should be in Hebrew. | Low | Medium | 2 | Country HR lead, Israel | Confirm in Mobilize whether any collective agreement or representative union covers the Israeli entity. Publish Hebrew versions of core policies alongside the English text, base the bylaw on the regulations' template, and avoid launch dates on Jewish holidays. | A union gives notice of representation, or a Hebrew version is not ready on the wave live date. | Open
R22 | NLRA exposure in US handbook rules | Under Stericycle, which remains binding, confidentiality, social media, recording, civility and media-contact rules must be narrowly tailored and carry a Section 7 savings clause. The NLRB may overrule these precedents during the program, so US policies could need rework in either direction. | Medium | Medium | 4 | Employment counsel | Add an NLRA check to Legal review for every US policy with conduct rules, use a standard savings clause, and review the NLRB watchlist item in the monthly legal change scan. | An NLRB decision overrules Stericycle or related precedent, or an unfair labor practice charge cites an Atlas policy. | Open
R23 | Low adoption of Atlas by contributors | If owners keep drafting in email and local files, Atlas status will be wrong, approvals will happen outside the chains and evidence will be missing at audit. | Medium | Medium | 4 | HR Program Manager | Make Atlas the only route to approval, with no sign-off by email. Train owners with V2 and V3 before Wave 1, hold weekly office hours and report each workstream's Atlas activity at status meetings. | More than 20% of in-flight items show no Atlas activity for three weeks. | Open
Score = likelihood (1 low, 2 medium, 3 high) x impact (same scale). 6 or more is a high risk on the dashboard and status report.

## Issues
ID | Issue | Detail | Priority | Owner | Action | Due | Status
I01 | Approver roster incomplete | Country HR lead steps for several jurisdictions and the delegates for Regional HR review have no confirmed incumbent, so the chains cannot be tested end to end before M03. | High | HR Program Manager | Regional HR leads confirm a primary and a delegate for every country step; PMO runs the test submission as soon as the roster is complete. | 2026-10-28 | Open
I02 | Current documents spread across many locations | Existing policies and procedures sit in intranet pages, the HRIS document library, country shared drives and email, with no index, which blocks the current-state rating needed for the baseline (M04). | High | HR Program Manager | Run a two-week document sweep with each workstream and region and load every version found into Atlas against its item. | 2026-11-04 | Open
I03 | No agreed owner for deemed export controls | Trade Compliance and Talent Acquisition each expect the other to own the export-control role flag and the start-date gate, so these semiconductor items have no owner for the baseline. | High | Director, Talent Acquisition Operations | Bring a proposed RACI to the steering committee for decision, with Trade Compliance accountable for license determinations. | 2026-10-23 | Open
I04 | Translation vendor not under contract | Procurement needs 4 to 6 weeks for a new vendor, but Wave 1 needs its first translated drafts in mid-January 2027. | Medium | HR Change and Communications lead | Use the current vendor under its existing agreement for Wave 1 while procurement runs, and agree the glossary and turnaround in writing. | 2026-11-13 | Open
I05 | Local counsel not engaged in Taiwan and Vietnam | Wave 1 includes a Taiwan work rules amendment and a Vietnam internal labour regulations registration, and neither country has engaged local counsel. | Medium | Employment counsel | Engage local counsel in both countries on a fixed-fee bundle covering the work rules filing, the ILR dossier and Wave 1 addenda. | 2026-11-20 | Open

## Assumptions
ID | Assumption | Owner | Validate by
A01 | The 438 library items (57 policies, 97 processes, 284 legal obligations) are the full scope; new items enter only through change control. | HR Program Manager | 2026-11-06
A02 | Workstream leads and regional HR leads can give at least 20% of their time from kickoff to 13 Aug 2027, with the time protected in the charter. | Chief People Officer | 2026-10-23
A03 | Employment counsel, with a local counsel panel, can review 25 to 30 items a week at the Wave 1 peak. | Employment counsel | 2026-11-06
A04 | Whether an elected works council exists at each German establishment is confirmed in Mobilize; where none exists, German items skip policy chain step s5 with a note. | Country HR lead, Germany | 2026-10-30
A05 | Darwinbox stays the HRIS of record for the whole program, and the HRIS team can deliver configuration changes in monthly release windows. | Director, HRIS and People Analytics | 2026-11-06
A06 | Headcount thresholds that drive local duties are confirmed per entity and site, for example Taiwan 30+ (work rules filing), Israel 25+ (sexual harassment bylaw), Vietnam 10+ (registered internal labour regulations) and India 10+, 20+ and 300+ (POSH committee, grievance committee, standing orders). | Regional HR leads (Americas, EMEA, APAC) | 2026-11-06
A07 | One translation vendor can cover German, Hebrew, Simplified and Traditional Chinese, Vietnamese, Kannada, Telugu and Spanish within 10 business days per batch. | HR Change and Communications lead | 2026-11-13
A08 | Every employee, including lab and operations staff, has a corporate login that lets them read published policies and complete acknowledgments. | Director, HRIS and People Analytics | 2026-11-20
A09 | China and Vietnam entities have union or employee representative structures able to run consultation in January 2027. | Regional HR lead (APAC) | 2026-11-20
A10 | Internal Audit accepts Atlas approval records and published versions as evidence for SOX-relevant HR controls. | HR Program Manager | 2026-12-11
A11 | No reorganisation, acquisition or reduction in force during the program year is large enough to require re-sequencing the waves. | Chief People Officer | 2027-02-12

## Decisions
ID | Decision | Detail | Owner | Status | Due
D01 | Policy repository of record | Atlas is the single repository of record for every policy, process and obligation, with version history and approvals. Intranet pages and HRIS links point to the Atlas published version, and local copies are retired at Go live. Where a local text is the binding version (China handbook, Taiwan work rules, Vietnam internal labour regulations, Germany works agreements), Atlas holds it as the country document. | Chief People Officer | Proposed | 2026-10-23
D02 | Global policy with country addenda | Each policy is one global document with a country addendum wherever local law adds or changes requirements. Separate local documents are used only where the law requires them: Germany works agreements, the China employee handbook, Taiwan work rules, Vietnam internal labour regulations, India standing orders or service rules and the Israel sexual harassment prevention bylaw. | Employment counsel | Proposed | 2026-10-23
D03 | Approval chain design | Five role-based chains: global policy (6 steps), process document (4), legal obligation (3), public company and semiconductor control (3) and project document (3). Employee representative consultation is an optional policy step recorded with an outcome or a skip note. Every step has a named primary and delegate. | HR Program Manager | Agreed | 2026-10-30
D04 | Translation vendor and prevailing language | Select one translation vendor for German, Hebrew, Simplified and Traditional Chinese, Vietnamese, Kannada, Telugu and Spanish, working from an HR and legal glossary. English is the master text except in China, Taiwan and Vietnam, where the local text prevails because courts and authorities rely on it. The Country HR lead signs off each translation. | HR Change and Communications lead | Proposed | 2026-11-06
D05 | Wave sequencing method | Rank items by legal, public-company and semiconductor risk, then by current-state rating. Each workstream delivers about 40% of its required items in Wave 1, 35% in Wave 2 and 25% in Wave 3, and best-practice items go to Wave 4. Policies come before the processes, notices and controls that depend on them. | HR Program Manager | Agreed | 2026-11-06
D06 | Effective-date convention | Global effective dates fall on the 1st or 15th of a month, at least 10 business days after final approval and never inside a holiday freeze. Where consultation, filing or registration is required (Germany, China, Taiwan, Vietnam), the country addendum states a later local effective date and the policy applies there only from that date. | Employment counsel | Proposed | 2026-10-30
D07 | Attestation and acknowledgment tool | Choose between the Darwinbox acknowledgment workflow and a separate attestation platform for wave acknowledgments and the September 2027 global campaign. Criteria: reach to every employee including lab staff, local-language support, acknowledgment records accepted in China and Vietnam, manager reporting and an audit trail. | Director, HRIS and People Analytics | Proposed | 2026-11-20
D08 | Document template standard | Policies use the library policy template (T-POLICY) with purpose, scope, policy statements, roles, country addenda, related items, owner and review date. Processes use a map, steps, controls and a RACI. Obligations use the register fields: requirement, owner, cadence, citation and evidence. All documents use plain English, sentence case and roles rather than names. | HR Program Manager | Agreed | 2026-10-30
D09 | Item ownership model | Every item has one accountable owner role, one workstream and a backup. Obligations keep the functional owner shown in the register (for example Trade Compliance or Payroll), with the workstream lead as coordinator. | Chief People Officer | Proposed | 2026-11-06
D10 | Legal review tiering and local counsel model | Three tiers: full review with local counsel for items with addenda in Germany, Israel, India, Taiwan, China and Vietnam; full in-house review for US and Canada policies; light review for processes without legal content. Local counsel work on fixed-fee bundles per wave. | Employment counsel | Proposed | 2026-11-06
D11 | Germany works council approach | If a works council exists, agree one framework works agreement for Atlas with an annex per co-determined topic (conduct, working time and recording, IT and monitoring tools, pay and bonus principles, mobile work) rather than separate agreements per policy, and decide which existing works agreements stay in force. | Regional HR lead (EMEA) | Proposed | 2026-11-27
D12 | Evidence standard per stage | Define what closes each stage: current-state record (Discover), template-complete draft (Draft), resolved comment log (Review), approval chain record (Approve), and the published version with its communication, training or posting record, plus consultation minutes, filing receipt or registration where required (Go live). Internal Audit confirms it can sample against this standard. | HR Program Manager | Proposed | 2026-11-06
D13 | Personal data in Atlas | Atlas holds documents and completion evidence, not employee records. Evidence that contains personal data stays in the system of record and is linked, samples are redacted, access is role-based and a retention rule is agreed with the Privacy Office. | Director, HRIS and People Analytics | Proposed | 2026-10-30
D14 | Change control for scope and new laws | New items, or major rework caused by a law change, enter the plan only through a change request that shows the impact on wave dates and resourcing. The PMO reviews it and the steering committee decides, using the project document chain. | Chief People Officer | Proposed | 2026-10-23

## RACI
Activity | Sponsor | SteerCo | PMO | WS lead | Item owner | Legal | Regional HR | Comms | Internal Audit
Approve charter, scope, budget and governance (M02) | A | R | R | C | I | C | C | I | I
Maintain plan, RAID log and status reporting | I | I | R/A | C | I | C | C | I | I
Configure and test approval chains (M03) | I | I | R/A | C | I | C | C |  | C
Confirm owners, current-state ratings and waves (M04) | I | C | R | A | R | C | C | I | I
Discover: find current documents and rate gaps | R: I; A: C; R: R/A; C: C; C: R
Draft global text in the standard template |  |  | I | C | R/A | C | C | I
Draft country addenda and arrange translation |  |  | I | I | C | C | R/A | I
Legal review and local counsel engagement | R: I; A: I; R: C; C: R/A; C: C
Employee-representative consultation and local filings |  | I | I | I | C | C | R/A | C
Final approval of global policies and effective dates | A | I | I | R | R | R | R | I
Publish approval of process documents (Head of HR Operations) |  |  | I | R/A | R | C | C | I | C
Sign-off of legal obligation evidence | R: I; A: I; R: R; C: A; C: R
Approval of public-company and semiconductor controls (General Counsel or delegate) |  | I | I | C | R | A |  |  | C
Publish, communicate and mark items live |  |  | R | C | A | I | R | R
Communications calendar, manager toolkits and training | I |  | C | C | C | I | C | R/A
Global attestation campaign (M15) | C | I | R | I | C | C | R | A | I
Approve change requests outside PMO tolerance | C | A | R | C | I | C | C | I
Audit readiness review (M16) | I | I | R | C | C | C |  |  | R/A
Handover to business as usual (M17) | I | I | A | R | R |  | C | I
Close-out report and lessons learned (M18) | A | R | R | C | I | C | C | C | C

## Approval chains
Chain | Applies to | Step | Step name | Role | Must sign | Optional | Guidance | Named approvers
Global policy | Policies | 1 | Owner sign-off | Policy owner | Any | No | Confirms the draft is complete, uses the standard template and has every country addendum.
Global policy | Policies | 2 | Workstream review | Workstream lead | Any | No | Checks consistency with related policies and processes.
Global policy | Policies | 3 | Legal review | Employment counsel | Any | No | Confirms legal requirements are met in every jurisdiction; engages local counsel where needed.
Global policy | Policies | 4 | Regional HR review | Regional HR leads (Americas, EMEA, APAC) | All | No | Each region confirms the addenda are workable and flags consultation or filing needs.
Global policy | Policies | 5 | Employee representative consultation | Country HR lead | Any | Yes | Required where works councils or employee representatives have rights (Germany, China, Vietnam, Taiwan filings). Record the outcome; skip with a note where not needed.
Global policy | Policies | 6 | Final approval | Chief People Officer | Any | No | Approves publication and the effective date.
Process document | Processes | 1 | Process owner sign-off | Process owner | Any | No | Confirms the flow matches how work is actually done, including exceptions.
Process document | Processes | 2 | Workstream review | Workstream lead | Any | No | Checks hand-offs with other processes and the governing policy.
Process document | Processes | 3 | Control review | Internal Audit or SOX PMO | Any | Yes | Required when the process contains a key or SOX-relevant control.
Process document | Processes | 4 | Publish approval | Head of HR Operations | Any | No | Approves publication and confirms systems and training are ready.
Legal obligation | Filings, notices, programs, trainings, records and committees | 1 | Owner sign-off | Item owner | Any | No | Confirms the obligation is met and evidence is filed.
Legal obligation | Filings, notices, programs, trainings, records and committees | 2 | Legal and compliance review | Employment counsel or Compliance | Any | No | Confirms the evidence satisfies the requirement and the next due date is set.
Legal obligation | Filings, notices, programs, trainings, records and committees | 3 | Country HR confirmation | Country HR lead | Any | No | Confirms local completion, language and posting or filing.
Public company and semiconductor control | Public-company and semiconductor items | 1 | Owner sign-off | Control owner | Any | No | Confirms design and evidence.
Public company and semiconductor control | Public-company and semiconductor items | 2 | Compliance review | SOX PMO or Trade Compliance | Any | No | Confirms the control is designed effectively and testable.
Public company and semiconductor control | Public-company and semiconductor items | 3 | Executive approval | General Counsel or delegate | Any | No | Approves for audit and disclosure purposes.
Project document | Charter, plan and change requests | 1 | PMO review | HR Program Manager | Any | No | Confirms the document is complete and consistent with the plan.
Project document | Charter, plan and change requests | 2 | Steering committee | Steering committee members | Any | No | Any steering committee member may record the committee's decision.
Project document | Charter, plan and change requests | 3 | Sponsor approval | Chief People Officer | Any | No | Final approval.

## Country gates
Jurisdiction | Consultation | Filing or registration | Language | Lead time | Notes | Verify
United States — Federal (+ multi-state) | None required: there are no works councils. Check every handbook rule against NLRA Section 7: under Stericycle (still binding), confidentiality, social media, recording, civility and media-contact rules must be narrowly tailored with a savings clause, whether or not a union exists. | None for HR policies. Separate public-company duties: the Code of conduct must be publicly available with executive waivers disclosed (Nasdaq), and insider trading policies are filed with SEC reports or their absence explained. | English. No federal language mandate for handbooks; English-only rules need business necessity. State rules decide translated notices. | 1 to 2 weeks after final approval to publish, set up acknowledgment and brief managers. No statutory waiting period. | Federal floor only; the work state drives most addenda. Where a handbook exists it must describe FMLA rights (50+ employees). Evidence is the handbook acknowledgment with state addenda.
California | None (NLRA only, no works councils). The Workplace Violence Prevention Plan must be developed with employee involvement. The SB 399 captive-audience ban is preliminarily enjoined. | None for HR policies. The annual CRD pay data report (100+ employees, due the second Wednesday of May) is a separate obligation. | Translate EEO and harassment policies into any language spoken by 10% or more of a facility's workforce (2 CCR 11023); Spanish is the likely trigger at some sites, depending on site workforce data (verify). Give the LC 2810.5 notice in the language normally used with the employee and the SB 294 notice in the employee's usual work language where a state template exists. | 2 to 4 weeks, mainly for translation and acknowledgment. The Workplace Know Your Rights notice is due at hire and by 1 Feb each year. | Handbooks must describe CFRA and PDL rights (5+ employees). No non-competes or non-California law or forum clauses. Watch CCPA automated decision-making duties from 1 Jan 2027 and SB 947 (operative 1 Jul 2027 if signed).
Colorado | None (NLRA only, no works councils). | None for HR policies. State EEO-1 filing rules (HB 26-1207) are expected late 2026, with a first filing in 2027. | Paid sick leave (HFWA) notice in English and any language spoken by 5% or more of the workforce; FAMLI notices in English and Spanish. | 2 to 3 weeks, mainly for Spanish and other translations. Refresh COMPS and PAY CALC figures in the Colorado addendum each 1 January. | Colorado addenda cover the POWR Act harassment program and complaint repository, job posting and promotion notices, biometric and data-disposal policies. SB 26-189 AI notices apply from 1 Jan 2027 to tools that materially influence employment decisions.
North Carolina | None. Right-to-work state; the NLRA governs and there are no consultation duties. | None for HR policies. | No statutory language requirement. NCDOL publishes Spanish posters; giving wage notices in a language the employee understands is best practice. | Wage-related policies (PTO, bonus, commission, deductions) must be given to employees in writing or posted before they can be enforced, and any change that reduces wages or wage benefits needs written notice at least one full pay period ahead. Plan 2 to 3 weeks. | State vacation forfeiture terms in writing. NC session laws often take effect on 1 Jul, 1 Oct or 1 Dec.
Texas | None. Right-to-work state; the NLRA governs and there are no consultation duties. | None for HR policies. | Workers' compensation coverage notices posted in English, Spanish and any other language common to the workforce. Deduction authorizations and policies in a language the employee understands. | 1 to 2 weeks. Vacation, holiday, sick and severance pay are owed only under a written agreement or policy, so publish the policy before relying on its terms. | Texas addenda cover the Payday Law, CUBI biometric notice, firearms in parking areas and the ban on COVID-19 vaccine mandates. The 2027 regular session runs Jan to Jun, and most new laws take effect 1 Sep 2027, inside Wave 4.
Washington State | None (NLRA, no works councils). Mandatory meetings on unionization are banned (RCW 49.44.250). Locations with 11+ employees on the same shift need an elected safety committee; involve it in Accident Prevention Program changes. | None for HR policies. | No translation mandate for contracts or handbooks. I-9 inspection notices (from 1 Oct 2026) go out in English and the five most common other languages in Washington. | 1 to 2 weeks. New laws usually take effect about 90 days after the session and rates change each 1 January; the noncompete ban starts 30 June 2027. | Seattle addenda cover Paid Sick and Safe Time, SMC 14.04 protected classes and the commuter benefit. Agreements need Silenced No More carve-outs.
Canada: Toronto (Ontario) and Vancouver (British Columbia) | None outside unionized workplaces. The Ontario workplace harassment program is developed with the joint health and safety committee or representative (JHSC at 20+ workers); BC has a joint committee at 20+ workers. | None for HR policies. | English for Ontario and BC. French only if there are Quebec-based employees, including remote staff: then contracts, policies and written communications must be in French (Bill 96), and 25+ Quebec employees triggers OQLF registration. | Ontario employers with 25+ employees on 1 Jan need disconnecting-from-work and electronic monitoring policies by 1 March, with copies to employees within 30 days. Harassment, violence and health and safety policies are posted and reviewed annually. Plan 3 to 5 weeks. | Toronto and Vancouver addenda. AODA accessibility policies must be documented at 50+ employees. BC requires a bullying and harassment policy with reporting and investigation procedures.
Germany (with EU layer) | Where a works council exists (possible at 5+ employees), policies on conduct rules, working time, IT and monitoring tools (including the HRIS, M365 and DLP), pay and bonus principles, mobile work and health protection must be adopted as works agreements (BetrVG §§77, 87(1) nos.1, 2, 3, 6, 10, 11, 14), not unilaterally. The council can enjoin a unilateral rollout, and disputes go to the Einigungsstelle. | None with an authority for HR policies. Works agreements must be made available to staff (§77(2) BetrVG), and statutory postings (ArbZG, AGG with the complaint office) go on the intranet or in the workplace. | German or bilingual versions of core policies for employees who are not fluent in English. Works agreements and works council communications are in German. | Where a works agreement is needed, plan 8 to 16 weeks from opening consultation to signature (planning estimate), and longer if the Einigungsstelle is called. Otherwise 2 to 4 weeks for German translation. Wave 1 consultations start by 29 Jan 2027 (M07). | Confirm in Mobilize whether a works council exists at each establishment. Works agreements must meet GDPR in full (CJEU C-65/23; BAG 2025 Workday damages). German pay transparency law missed the 7 June 2026 deadline, with a bill expected early 2027; AI Act employment duties apply from 2 Dec 2027.
Israel | No works councils. Where a collective agreement or representative union applies, policy changes affecting employment conditions must be negotiated. Avoid US-style messaging during any organizing, which courts treat as unlawful interference. | None for HR policies. The Section 102 equity sub-plan is filed with the Israel Tax Authority at least 30 days before the first grant (separate obligation). | Hebrew for statutory notices, the sexual harassment prevention bylaw and workplace postings, with Arabic or another language where employees need it. English policies are valid if understood, but publish Hebrew versions of core policies. | 3 to 5 weeks for Hebrew translation, posting and distribution; longer where a collective agreement requires negotiation. Avoid launch dates on Jewish holidays and Fridays. | Employers with 25+ employees must adopt a sexual harassment prevention bylaw based on the regulations' template, post it and give it to employees; every employer appoints a trained commissioner. Monitoring needs a written policy communicated in advance. The discipline policy needs a pre-dismissal hearing step.
India | No works council. Standing orders are certified, or the model standing orders adopted, at 300+ workers; the Karnataka IT/ITeS exemption was issued under the repealed 1946 Act and its status under the IR Code is unconfirmed (verify). A Grievance Redressal Committee is needed at 20+ workers and a POSH Internal Committee at 10+ employees. | POSH annual report to the District Officer. Standing orders certification where 300+ workers and no valid exemption. Units using the Karnataka exemption report suspensions, terminations and other disciplinary actions to the Deputy Labour Commissioner. | English for policies. Statutory notices and abstracts are displayed in English and the local language (Kannada in Karnataka, Telugu in Telangana), and the POSH policy and Internal Committee details are displayed in both. | 4 to 6 weeks for local-language display and committee updates. Standing orders certification takes longer (verify). Karnataka and Telangana rules under the Codes are still largely in draft. | The Labour Codes took effect on 21 Nov 2025 and central rules were finalised on 8 May 2026. DPDP notice and consent duties start 13 May 2027, inside Wave 2. Whether engineers are 'workers' or 'employees' decides standing orders, grievance committee and retrenchment coverage. | Yes
Taiwan | Labor-management meetings must be held at least quarterly with equal numbers of elected employee representatives; their consent is needed for overtime, flexible working hours and shift-rest changes where there is no union. | With 30+ employees, work rules are submitted to the local labor authority (the Science Park Bureau for Hsinchu Science Park sites) for approval, posted, and refiled on every amendment. Global policies are not enforceable locally unless incorporated into the work rules. | Traditional Chinese for work rules filed with the authority, notices and labor-management meeting materials. Bilingual policies are recommended; courts and inspectors rely on the Chinese version. | 6 to 10 weeks for translation, the quarterly labor-management meeting where consent is needed and authority review; the authority's review time is not confirmed in the library (verify). Lunar New Year freeze 5 to 14 Feb 2027. | Sexual harassment and workplace bullying rules (complaint channel at 10+, prevention, complaint and discipline rules at 30+) belong in the work rules. File one consolidated amendment per wave.
China (Mainland) | Democratic procedure (Labor Contract Law Art. 4): rules on pay, hours, leave, safety, discipline and training are discussed with the employee congress or all employees, finalised after consultation with the union or employee representatives, and publicised with signed acknowledgment. Without it they cannot support an Art. 39 dismissal. | No authority filing for the handbook. Special working-hour systems need local HR bureau approval, and the overseas parent's equity plans need SAFE registration before employees participate (separate obligations). | Bilingual handbook and policies with the Chinese text prevailing; labor bureaus, arbitration commissions and courts work in Chinese. | 6 to 8 weeks per consolidated procedure (planning estimate) for discussion, consultation, publication and acknowledgment. Adopt annual changes before 1 Jan, and hold no meetings during the Lunar New Year freeze (5 to 14 Feb 2027). | Shanghai and Shenzhen rules differ on sick pay, leave and social insurance. Shanghai sick pay now follows contract or handbook terms after the old notices lapsed on 15 Aug 2026, which makes the sick leave policy a Wave 1 priority. Keep notices, sign-in sheets, comment logs, minutes and acknowledgments as evidence.
Vietnam | Consult the grassroots trade union (where one exists) before issuing or changing internal labour regulations (ILR), salary scales, bonus rules and performance criteria; workplace dialogue is also required before ILR changes. | Employers with 10+ employees register the ILR with the provincial Department of Home Affairs (Hanoi, Ho Chi Minh City) within 10 days of issue. ILR take effect 15 days after the authority receives a complete dossier and must be posted at the workplace; branches in other provinces send the registered ILR to their local authority. | Vietnamese for ILR, labour contracts, disciplinary minutes and filings. Bilingual versions are allowed for foreign employees, but authorities and courts work from the Vietnamese text. | 6 to 8 weeks: union consultation and dialogue, translation, registration within 10 days of issue and the 15-day period before effect. Tet freeze 5 to 14 Feb 2027. | Discipline is valid only on grounds in the registered ILR, so fold Code of conduct consequences, the sexual harassment section and secret-protection clauses into the ILR. Add a clause on cross-border HR data flows so the Decree 356 HR-management exemption applies.

## Comms
ID | Date | Wave | Type | Audience | Message | Channel | Owner
C01 | 2026-10-12 | W0 | Announce | Sponsor, workstream leads, regional HR leads, Employment counsel and PMO | Kickoff: purpose, scope (438 items in 13 jurisdictions), the five waves, roles and the four weeks of Mobilize. | Kickoff meeting (video, recorded) | Chief People Officer
C02 | 2026-10-14 | W0 | Announce | All HR, Legal, Payroll and People Operations staff | Project Atlas announced: what it is, why now, how the work runs in waves and what people will be asked to do. Watch V1. | Email from the Chief People Officer and HR all-hands | HR Change and Communications lead
C03 | 2026-10-19 | W0 | Engage | Item owners | You are the named owner for these items: confirm ownership, current documents and a backup by 30 Oct. Watch V2. | Atlas task notification and email | HR Program Manager
C04 | 2026-10-21 | W0 | Train | Approvers in all five chains | Your chain steps, response targets and delegates, and the end-to-end test submission before 30 Oct (M03). Watch V4. | Approver briefing (video call) | HR Program Manager
C05 | 2026-10-27 | W0 | Train | Regional and country HR leads | Country gates: consultation, filing, language and lead time in each jurisdiction, and how they set local effective dates. Watch V5. | Regional HR calls (Americas, EMEA, APAC) | Regional HR leads (Americas, EMEA, APAC)
C06 | 2026-11-06 | W0 | Announce | Steering committee, workstream leads and regional HR leads | Mobilize gate (M04): every item has an owner, a rating and a wave; plan v1.0 is baselined and the Wave 1 list is confirmed. | Steering committee meeting and status email | HR Program Manager
C07 | 2026-11-09 | W1 | Announce | Wave 1 item owners and SMEs | Wave 1 starts: Discover workshops over the next two weeks, drafts due 18 Dec. Watch V3. | Email and Atlas notifications | Workstream leads
C08 | 2026-11-17 | W1 | Engage | German works council (where one exists) | Information on the Atlas scope, the Wave 1 items that touch co-determined topics and a proposed timetable for a framework works agreement. | Works council meeting with a German written summary | Country HR lead, Germany
C09 | 2026-12-07 | W1 | Remind | Wave 1 item owners, approvers and Legal reviewers | Wave 1 drafts are due 18 Dec (M06). The year-end freeze runs 21 Dec to 1 Jan with no approvals or launches; approvals restart on 4 Jan. | Email and Atlas dashboard | HR Program Manager
C10 | 2027-01-06 | W1 | Engage | Employees and employee representatives in China and Vietnam | Consultation opens on Wave 1 changes: the China democratic procedure on handbook changes and Vietnam union consultation on internal labour regulations, with bilingual drafts and meeting dates. | Employee and union meetings with bilingual notices | Regional HR lead (APAC)
C11 | 2027-01-13 | W1 | Engage | Taiwan labor-management meeting representatives | Wave 1 items that need labor-management meeting consent (overtime and flexible hours) and the planned work rules amendment filing. | Labor-management meeting with Traditional Chinese materials | Country HR lead, Taiwan
C12 | 2027-01-27 | W1 | Announce | All employees | Coming in February: a refreshed Code of conduct and the first core policies in Atlas, what changes and what you will be asked to acknowledge. | Intranet news and email | HR Change and Communications lead
C13 | 2027-02-01 | W1 | Train | People managers | Wave 1 manager toolkit: what changed, talking points, FAQ by country and how to track your team's acknowledgments. | Manager toolkit email and 30-minute live briefing | HR Change and Communications lead
C14 | 2027-02-03 | W1 | Announce | Employees in China, Taiwan and Vietnam | Before Lunar New Year and Tet: Wave 1 policies are approved globally; local effective dates follow consultation, filing and registration and will be posted after the holiday. | Local email in Chinese and Vietnamese | Regional HR lead (APAC)
C15 | 2027-02-11 | W1 | Announce | Employees in Israel | Wave 1 is live in Israel with Hebrew versions, the reissued sexual harassment prevention bylaw and the commissioner's contact details. | Hebrew and English email, intranet and workplace postings | Country HR lead, Israel
C16 | 2027-02-12 | W1 | Announce | All employees in the US, Canada and India, and in Germany for items outside co-determination | Wave 1 is live (M08): global policies published with a summary of what changed and the acknowledgment request, due in two weeks. Country-specific items follow on the dates in each addendum. | Intranet, email and Atlas acknowledgment request | HR Change and Communications lead
C17 | 2027-02-12 | W1 | Celebrate | Atlas contributors and steering committee | Wave 1 done: thanks from the sponsor, results against plan and the invitation to the wave retrospective. | Email from the Chief People Officer and team call | Chief People Officer
C18 | 2027-02-16 | W2 | Announce | Wave 2 item owners and SMEs | Wave 2 starts: Discover workshops this week and next, drafts due 9 Apr (M10). | Email and Atlas notifications | Workstream leads
C19 | 2027-02-24 | W2 | Announce | Employees in Ontario and British Columbia | Canada-specific Wave 1 items live: updated Ontario disconnecting-from-work and electronic monitoring policies, harassment and violence policies posted, and the BC bullying and harassment policy. | Email with policy copies and site postings | Regional HR lead (Americas)
C20 | 2027-03-03 | W2 | Announce | Employees in India (Karnataka and Telangana) | India-specific Wave 1 items live: POSH policy and Internal Committee details displayed in English and Kannada or Telugu, grievance committee contacts and the updated leave and holiday policy. | Email, intranet and office notice boards | Country HR lead, India
C21 | 2027-03-15 | W2 | Announce | Employees in China, Taiwan and Vietnam | Wave 1 local launch: China handbook changes published for signed acknowledgment, Vietnam internal labour regulations in effect after registration and posted, Taiwan work rules posted once approved. | Local all-hands, bilingual notices and workplace postings | Regional HR lead (APAC)
C22 | 2027-03-22 | W2 | Remind | Wave 2 item owners | Reminder: Wave 2 drafts are due 9 Apr (M10); items needing translation or consultation should be in Review now. | Email and Atlas dashboard | HR Program Manager
C23 | 2027-04-19 | W2 | Announce | Employees in Germany | Where a works agreement was needed, co-determined Wave 1 policies (working time recording, IT and monitoring tools, mobile work) take effect on the date agreed with the works council, with German versions. | German email, intranet and works council notice | Country HR lead, Germany
C24 | 2027-05-03 | W2 | Train | People managers | Wave 2 manager toolkit: core lifecycle processes going live and what changes for hiring, onboarding, leave and pay questions. | Manager toolkit email and 30-minute live briefing | HR Change and Communications lead
C25 | 2027-05-14 | W2 | Announce | All employees | Wave 2 is live (M11): core lifecycle processes and country addenda published; acknowledgment requested only for changed policies. | Intranet, email and Atlas acknowledgment request | HR Change and Communications lead
C26 | 2027-05-17 | W3 | Announce | Wave 3 item owners and SMEs | Wave 3 starts: the last required items, drafts due 9 Jul (M13). Rewatch V3 for process documents. | Email and Atlas notifications | Workstream leads
C27 | 2027-06-28 | W3 | Remind | Wave 3 item owners and approvers | Reminder: Wave 3 drafts are due 9 Jul and approvals must close by early August for go-live on 13 Aug. | Email and Atlas dashboard | HR Program Manager
C28 | 2027-08-02 | W3 | Train | People managers | Wave 3 manager toolkit: the remaining required policies going live and the plan for the September attestation campaign. | Manager toolkit email and 30-minute live briefing | HR Change and Communications lead
C29 | 2027-08-13 | W3 | Celebrate | All employees, Atlas contributors and steering committee | Every legal, public-company and semiconductor item is live with evidence (M14): thanks and results. | Email from the Chief People Officer, intranet story and team celebration | Chief People Officer
C30 | 2027-08-16 | W4 | Announce | Item owners and future business-as-usual owners | Wave 4 starts: best-practice items, evidence clean-up, audit readiness and handover, and how annual reviews will work. | Email and owner call | HR Program Manager
C31 | 2027-09-10 | W4 | Announce | All employees, in local languages | Global attestation campaign (M15): acknowledge the updated Code of conduct and core policies by 24 Sep. | Attestation tool, email and intranet | Head of Employee Relations
C32 | 2027-09-17 | W4 | Remind | Employees who have not attested, and their managers | Reminder: attestation closes 24 Sep; managers have completion dashboards for their teams. | Email, manager dashboard and HRBP follow-up | Head of Employee Relations
C33 | 2027-10-01 | W4 | Engage | Business-as-usual owners | Handover complete (M17): your items, review dates and annual review calendar, and how to raise a change. | Email and Atlas owner view | HR Program Manager
C34 | 2027-10-08 | W4 | Celebrate | Atlas contributors, steering committee and HR | Project close (M18): close-out report, lessons learned and thanks from the sponsor. | Email from the Chief People Officer and closing call | Chief People Officer

## Training
ID | Module | Audience | Format | Length | Objectives | Video
TR1 | Project Atlas orientation | Everyone working on Atlas: item owners, approvers, workstream leads, regional HR, Legal and PMO | Self-paced video with a five-question check | 20 minutes | Explain the goal: 438 items live in 13 jurisdictions by 8 Oct 2027 Name the five stages and the five waves with their dates Know where to get help and how to raise a risk or issue | V1
TR2 | Find and update your items | Item owners and workstream leads | Live virtual demo with practice tasks | 45 minutes | Find your items and filter by wave, workstream and jurisdiction Update stage, status and current-state rating Attach evidence and link related items | V2
TR3 | Document a process in five steps | Process owners, SMEs and workstream leads | Workshop on a real Wave 1 process | 60 minutes | Map the process as it is actually done, including exceptions Write steps, controls and a RACI in the standard template Mark key and SOX-relevant controls for control review | V3
TR4 | Write a policy and its country addenda | Policy owners, workstream leads and regional HR | Workshop using the policy template (T-POLICY) | 60 minutes | Use the template sections and the plain-English standard Decide when a country addendum is needed, using the library research Flag consultation, filing and translation needs before Review
TR5 | Set up and run an approval chain | Approvers, workstream leads and Legal reviewers | Video plus live Q&A | 30 minutes | Know which chain applies to policies, processes, obligations, controls and project documents Approve, return or delegate a step and record the reason Meet the 3-business-day step target and escalate when blocked | V4
TR6 | Take a policy live in 13 countries | Regional HR leads, country HR leads and Legal reviewers | Live session run by region (Americas, EMEA, APAC) | 90 minutes | Apply each jurisdiction's gate: consultation, filing, language and lead time Plan local effective dates around consultation, registration and holiday freezes File consultation minutes, filing receipts and translations as evidence | V5
TR7 | Legal review in Atlas | Employment counsel and local counsel | Live virtual session | 45 minutes | Work the review queue by tier and target time Use the clause library, including the NLRA savings clause and whistleblower carve-outs Record legal sign-off and the next review date | V4
TR8 | Running a workstream | Workstream leads and PMO | Live workshop | 2 hours | Plan items across waves and stages and keep dates current Log risks, issues and decisions and escalate on triggers Prepare weekly status and steering committee inputs
TR9 | Explaining policy changes to your team | People managers | Live briefing, recorded, with a one-page toolkit | 30 minutes per wave | Explain what changed this wave and why Answer common questions and know where to send the rest Track your team's acknowledgments | V1
TR10 | Your policies and how to acknowledge them | All employees | Micro-learning in local languages, linked from the acknowledgment request | 10 minutes | Find the Code of conduct and core policies in Atlas Understand what an acknowledgment means and when it is due Know how to ask a question or raise a concern, including through the speak-up hotline | V1
TR11 | Evidence, audit readiness and handover | Item owners, control owners and PMO | Live virtual session with an evidence checklist | 45 minutes | Know what evidence closes each stage Prepare for the Internal Audit sample on 24 Sep 2027 Set the owner, review date and annual review slot for business as usual